## Previous
Category | Item | Discipline | Location | Observation | Consequence | Status comment | Current Status | Responsible person | Update Aug 2025
Mining, TSF, SHERQ, Clinic & Security | P1 | TSF | NCH 2 & Gloria | Small gullies on the old TSF's - NCH II-remining area and RWD at Gloria. | Wall instability. Maintain walls on the TSF and RWD's | Status June 2023: Open Improved, but currently no operator for the small excavator on site - ongoing maintenance required. Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P2 | Environmental | All areas | 1. No standard for oil spill kits. Different colours, no checklist (list of content), not sealed, different naming etc., 2. Other items in placed boxes. | Incorrect treatment of oil / chemical spillage. | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P3 | Environmental | All areas | Contaminated items in general waste and general waste items in hazardous waste bins. Topic for June is Waste Sorting, but this aspect needs to improve. | Poor hazardous waste management. | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P4 | Mining | Gloria - 98South/ 23West | Ore in hanging after blast, poor breaking - long sockets on the sides & bottom of face. Drilling and blasting practices need to improve. | FOG's. | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P5 | Mining | Gloria - 98South/ 23West | Water pool reported by nightshift, dayshift still making arrangements to pump. | Also report by DMRE on 21 April 2023. | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P6 | Mining | Gloria Lamp Room | Moved away from Booyco and is currently using Exsens gas testing device that cannot download info & must be manually calibrated. Waiting for project to test Ventis/DSX gas testing devices that can download info. | No means to check history after an incident. | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P7 | Mining | Gloria Lamp Room | GDI's only issued to miners 1. Procedure require miner to test before work commences. 2. Best practice is that GD'I must be at the working area whist work is taking place. 3. Boilermakers have recently been trained to use gas testing devices. | Possible gas explosions. | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P8 | Fire | Gloria surface area | Evidence of people smoking outside smoking areas & smoking areas used at buildings next to lamp room is not correctly demarcated - only a red pipe. | Fire risk | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
| P9 | Security | Gloria | Sabotage reportedly taking place at critical equipment such as the crusher lube room, vent fans, etc. Consider the installation CCTV at these critical susceptible areas. | Production delays | Status Oct 2024: Completed. No deviations observed during the site visit. | Completed
Fire Protection | P10 | Fire | Nchwaning 2; Fire Pump Station | The water level indicators at the fire water reservoirs appear faulty. Provide water level alarm to Scada. | Insufficient water for effective firefighting. | Status December 2021: Open. In progress. Water levels still to be alarmed to Scada. Thanks were noted to be 1/2 full. Status August 2022: Open. In progress. Will be alarmed to Scada by end of the year. Status June 2023: Open. In progress. All level indicators installed. Scada to be configured. Status October 2024: Completed. The water level alarm to Scada is installed and operational. | Completed
| P11 | Fire | Conveyor 15F | A fixed water spray system is been installed. Ensure that the contractor provides a commissioning certificate confirming the Code to which the system has been designed and installed i.e. NFPA 15. | Failure of protection to operate as intended. | Status August 2022: Open. Status June 2023: Open. No certificate availible, to be recommissioned. Status October 2024: Completed. Michael Bester to share commissioning documintation. | Completed
| P12 | Fire | Main Consumer Substation Generator Station Diesel Tank | Generator Station is supplied diesel from an 83 kl diesel tank. An Akron monitor and 1 kl AFFF foam tank has been provided. The monitor is however quite close to the diesel installation and in a fire situation radiant heat would possibly impede the manning of the monitor. We suggest that the monitor be relocated to at least 20/25m from the tank / alternatively a fire barrier wall be constructed to protect the monitor operator. | Flammable liquid fire. | Status June 2023: Open. In progress. Mine has requested a quotation from the supplier to move the monitor. Status October 2024: Open. | Open | M Mteki | tireleng provided calculations that shows the installation is within reasonable position
| P13 | Fire | Main Consumer Substation Generator Station Diesel Tank | Several of the pipe flanges are not bonded. Confirm that the electric motors are flameproof. Status June 2023: Open. Review current installation against the most recent editions of SANS 10089, part 1 & 2 and SANS 10108... In addition, the complete storage and distribution system must be audited... with electrical resistively not exceeding 10 Ω for static electricity charge dissipation. | Flammable liquid fire. | Status October 2024: Open. It was reported that this is scheduled to be done by service provider (Total Energies) in Q1 2025. | Open | M Mteki | Extra earth bonding done by African Fuel
| P14 | Fire | Main Consumer Substation - Generator Station Diesel Tank | The generators are fitted with Ansul fire suppression systems. Ensure that the diesel supply is interlocked to shut down on activation of an Ansul system. | Flammable liquid fire. If the diesel supply is not interlocked with the fire detection and suppression systems then there is a possibility that diesel would continue to flow into a fire situation and limit the effectiveness of the suppression systems. | Status June 2023: Open. Status October 2024: Open. | Open | M Mteki | Wired on the Generator safety circuit
| P15 | Passive fire protection | Gloria Surface Substation 10Υ | A section of the cable feed from the rack room to MCC101Y should be coated with intumescent paint and cable penetrations sealed. | Fire spread from rack room to MCC. | Status October 2024: Completed. | Completed
| P16 | Wildfire | NCH 2 MCC2 Load Out | Clear the overgrown grass which runs alongside the cable run leading from the MCC to the return water dam. . | Wildfire damaging cable run. | Status October 2024: Open. Ongoing | Open | M Bester | Area cleared of overgrown grass
| P17 | Fire Suppression | NCH2 MCC2 | 3 of the pyroshield cylinders were noted with release safety pins inserted. In a fire situation these cylinders would not activate (note that this was corrected at the time of the survey). | Failure of suppression system. | Status October 2024: Completed. | Completed
| P18 | Fire Suppression | Various substations both on surface and UG. | In numerous cases wiring to pyroshield pilot cylinder actuators were noted to have cable joints and taped with insulation tape. There should be no joints to activation cabling. | Failure of suppression system. | Status October 2024: Open. In progress. Mostly completed with move to electronic activation. Some cable joints taped with insulation tape still noted. | Open | Itireleng
| P19 | Fire Suppression | Gloria UG Workshops | The current 'sprinkler system' is not to standard and will not operate effectively. A project is in place to protect the workshop area with a fixed foam water system... Please confirm that design is to NFPA 16 or another similar approved/recognised Code/Standard... On commissioning of fire systems it is important ensure that the installer provides a certificate of inspection... | Failure of suppression system. | Status October 2024: Open. Installation is expected to be completed towards the end of 2025. | Open | S Dubazane
| P20 | Passive Fire Protection | Gloria UG Substation 98Y | Cable penetrations where piercing the fire wall are sealed with combustible polyurethane foam. It is recommended that an audit is conducted on service penetrations of fire walls and where necessary the correct sealing materials are used. | Fire spread into key utility areas. | Status October 2024: Open. In progress. | Open | S Dubazane
| P21 | Transformer Fire Protection | Gloria UG Substation 98Y Transformers | These 4 x transformers are old mineral oil transformers. Consider ester oil transformers... With a high flash point of 330°C they also provide a high level of fire safety compared to a flash point of 145°C for petroleum-based mineral oil. | A fire here would be difficult to extinguish with damage to property, consequent business interruption losses, and life and safety exposures. | Status October 2024: Open. In progress. Mine reports that these transformers are under low load. The intention is to replace the transformers with a Mini Substation. Smoke detection is now installed in this area. | Open | S Dubazane
| P22 | Conveyor Fire protection | Gloria UG 51H, 52H, 53H & 54H | These belts are fitted with a manually operated deluge system protecting the top belt only... No fire detection is fitted... Protection for underground conveyance systems should comply with the requirements of NFPA 15... Linear heat or Infra-Red fire detection should be installed... | Property damage and associated business interruption losses. | Status October 2024: Open. In progress. Mine reports that these belts are only in operation once per week. Belts will be replaced with Type F Fire Retardant belts. ETA is July 2025. Additional smoke detection has been installed in this area. | Open | S Dubazane
| P23 | Fire Suppression | Gloria Surface Decline MCC 90Y | One of the pyroshield cylinders showed low pressure. | Failure of fire suppression system. | Status October 2024: Completed | Completed
| P24 | Fire Suppression | Gloria Surface Decline MCC 90Y | Conduct a room integrity test. | Failure of fire suppression system. | Status October 2024: Open. | Open | Itireleng
| P25 | Fire Water Supplies | NCH3 Fire Pump House | The diesel drive fire pump packing gland is leaking excessively. This should be attended to. | Pump performance. | Status October 2024: Completed. | Completed
| P26 | Gas Storage | Stores | Combustible materials should not be stored alongside flammable gas and chlorine store. | Fire spread to gas store. | Status October 2024: Completed. | Completed
| P27 | Sprinkler | Stores | The flow gauge at the Blink 1 Cement Store ICV is damaged. | Failure to test water flows at ICV. | Status October 2024: Open. | Completed | M Mteki
Engineering | P28 | Electrical | Nchwaning 2 & 3 - 22KV yards | Main consumer substation has lightning arrestors installed. But no lightning arrestors installed on some overhead lines at other 22kV yards including NCH 3... | Lightning strikes may cause spike, surges and outages. | Status October 2024: Open. It was reported that this line will be replaced, ETA is end December 2024. | Closed | X Petersen | All incoming to Substations have lightning arrestors.
| P29 | Electrical | Surface N2 | 14 Transformers oil analysis show critical condition. Nine transformers showed excessive water and low dielectric strength. Five showed excess dissolved gases... | Transformer failure and consequent possible downtime. | Status October 2024: Open. Oil sampling was done in July 2024 with all purification reportedly complete, however oil analysis summary report for October 2024 shows 20 transformers as ""critical"" condition for the mine that require attention, 2 for N2 surface. | Closed | M Bester
| P30 | Electrical | Gloria | 4 Transformers oil analysis show critical condition. Transformers show excess dissolved gases... | Transformer failure and consequent possible downtime | Status October 2024: Open. Oil sampling was done in July 2024 with all purification reportedly complete, however oil analysis summary report for October 2024 shows 20 transformers as ""critical"" condition for the mine that require attention, 2 for Gloria surface and 4 for Gloria UG. | Open | S Dubazane
| P31 | Electrical | NCH 2 | 3 transformers oil analysis show ""Critical"" condition. Fan sub N2 TF02 2MVA shows excessive water and low dielectric strength... | Transformer failure and consequent possible downtime. | Status October 2024: Open. Oil sampling was done in July 2024 with all purification reportedly complete, however oil analysis summary report for October 2024 shows 20 transformers as ""critical"" condition for the mine that require attention, 2 for N2 surface and 0 for N2 UG. | Closed | X Petersen | Latest Oil Analysis Attached to File. Old Transformers removed. New 5MVA installed and old 500kVA removed.
| P32 | Electrical | NCH 3 | 4 Transformers oil analysis show critical condition... | Transformer failure and consequent possible downtime. | Status October 2024: Open. Oil sampling was done in July 2024 with all purification reportedly complete, however oil analysis summary report for October 2024 shows 20 transformers as ""critical"" condition for the mine that require attention, 2 for N3 surface and 5 for N3 UG. | Open | S Sease
| P33 | Structural | NCH 2- column adjacent to jaw crusher | Column plinth and metal structure showing signs of damage and corrosion. | If untreated could result in structure failure. | Status October 2024: Completed. | Completed
| P34 | Structural | NCH 2 - jaw crusher | Spalling concrete at base and side/s of structure... | If left untreated, will lead to concrete failure and possible structure collapse. | Status October 2024: Completed. | Completed
| P35 | Structural | NCH 2 - jaw crusher | Cracks in structure... | If left untreated, will lead to concrete failure and possible structure collapse. | Status October 2024: Completed. | Completed
| P36 | Electrical/ Fire | NCH 2-bulk diesel tank farm | Review current installation against the most recent editions of SANS 10089, part 1 & 2 and SANS 10108... Implement earthing and bonding protocols... | Non-compliant electrical installation for potentially hazardous locations. Sources of ignition can result in fire risk. | Status October 2024: Open. It was reported that this is scheduled to be done by service provider (TotalEnergies) in Q1 2025. | Open | M Mteki | Open, the COCs will be done once the new FMS is installed
| P37 | Mechanical | Main stores | Equipment stored on shelves, some packaging was open, and some packaging was missing... | Foreign material can enter equipment causing it to malfunction later. | Status October 2024: Open. Area not surveyed; however it was reported as status quo remains. | Open | M Mteki (Not my action) | Incorrectly located to my name
| P38 | Mechanical | NCH 3 underground- crusher discharge conveyor electromagnet | Currently no NDT testing is being done on support chains and turn buckles... | No early warning system in place for possible failure (single point of failure). | Status October 2024: Completed. Monthly visual inspections are conducted with records in Logbook, no further action to be taken in this regard. | Completed
| P39 | Electrical/ Fire | NCH 3 underground - bulk diesel storage | Pump set motor not compliant with hazardous area electrical classification for flammable liquids... | Unsafe condition, fire related risk. | Status October 2024: Open. It was reported that this is scheduled to be done by service provider (TotalEnergies) in Q1 2025. | Open | S Sease
| P40 | Safety | Main Stores | Stacking height to be checked to prevent items from falling of shelves... | Unsafe condition, possibly resulting in damage to property and injury to people if items fall off shelf. | Status October 2024: Completed. Ongoing maintenance of stacking required. | Completed
| P41 | Mechanical / Electrical | Main Stores | Spares lying open and unprotected... | Foreign material can enter equipment causing it to malfunction later. Damage to equipment. | Status October 2024: Open. Area not surveyed; however it was reported as status quo remains. | Open | M Mteki
| P42 | Mechanical | Main Stores | Fair number of hydraulic cylinders left lying horizontally on floor. Hydraulic cylinders should be stored in vertical position... | Rod and piston seal failure resulting in reduced lifespan of hydraulic cylinders, higher maintenance cost and more equipment downtime. | Status October 2024: Open. Area not surveyed; however it was reported as status quo remains. | Open | M Mteki
| P43 | Mechanical / environmental | NCH 2-seam 1 hydraulic room. | Bunding of power pack insufficient to contain large hydraulic fluid leak. | 1. Hydraulic fluid leak could result in localised soil contamination. 2. No early warning of hydraulic fluid loss from power pack reservoir, could result in equipment damage and plant downtime. | Status October 2024: Open. Status quo remains. It was reported that this will be addressed as part of an upgrade to this area. | Open | M Bester
| P44 | Electrical | Main stores. | Spare transformer leaking oil... | Not to standard, will result in transformer oil loss from new transformer, with possible moisture ingress into transformer, transformer damage. Localised ground contamination. | Status October 2024: Open. Area not surveyed; however it was reported that transformers are in bunded area with one transformer leaking, status quo remains. | Open | M Mteki | Within the Bunded Area, placed the order with TFS to repair
| P45 | Mechanical | Main stores. | Hydraulic cylinders being stored on their sides... | Not to standard, will result in damage to hydraulic seals resulting in premature seal failure and equipment downtime. | Status October 2024: Open. Area not surveyed; however it was reported as status quo remains. | Open | M Mteki
| P46 | Mechanical/ Safety | Main stores. | Racking rated to store heavy loads; no inspection certificate available for racking inspection... | Potentially unsafe condition, racking collapse resulting in injury and damage to equipment. | Status October 2024: Open. Area not surveyed; however it was reported as status quo remains. | Open | M Mteki - How can we do this rack test?
| P47 | Mechanical | Main stores. | Spare engine not covered... | Possible ingress of foreign material into engine resulting in damage. | Status October 2024: Open. Area not surveyed; however it was reported as status quo remains. | Open | M Mteki
| P48 | Electrical | Gloria mine UG substation 96 1 Y. | 1. Battery acid on BTU terminals. 2. No localised of relayed alarm in the event of BTU fault/failure. 3. Evidence of transformer gassing taking place... | 1. Possible battery acid leak... 2. No proactive warning of BTU fault condition... 3. Possible internal fault condition of transformer... | Status October 2024. 1. Completed. 2. Open-status quo remains. 3. Completed. Note: Main 22KV substation - BTU trip has SMS system... | Open | S Dubazane | Part of phase 2 on iROC to have BTU health display in control room (Dec 2026)
| P49 | Structure / Buildings | Gloria Underground Block 74 Explosive & Magazines Store | Water leaking from the roof of the room... | Investigate and implement discharging or diversion of water from the room. | Status October 2024: Completed. | Completed
| P50 | Structure / Buildings | Workshop Roof | The roof steel purlin is deformed, sagging formation due to the lifting of the roof... | Investigate the cause of roof deforming and repair. | Status October 2024: Completed. | Completed
| P51 | Electrical | N2-MCC1 | 1. BTU battery level low. 2. BTU not connected to SCADA... | Compromised BTU system resulting in compromised protection and tripping of circuit breakers. If a fault is detected the BTU trips the system to cut power to equipment before failure occurs. | Status October 2024. 1.Completed. 2. Open status quo remains. | Open | M Bester | Part of phase 2 on iROC to have BTU health display in control room (Dec 2026)
| P52 | Electrical | Gloria - surface 10Y sub, vent fans sub. N3-UG silo bottom sub | Electrical reticulation drawings not signed off... | Not to standard, incomplete records. | Status October 2024: Completed. All done. | Completed
| P53 | Electrical | N2-MCC2 | Spare breaker last serviced in June 2018 as per label on breaker... | Potential for compromised spare breaker. | Status October 2024: Completed. Breaker service in November 2023. | Completed
| P54 | Electrical | N2- 60EP40GE15 genset | Power cables from battery to starter motor not fully insulated at terminal points... | Not to standard, possibility of electric shock. | Status October 2024: Open. Status quo remains. | Open | X Petersen/M Bester | In progress. ETA end Sept 2025
| P55 | Electrical | N2-thickener sub transformer | Cooling radiator has a crack and transformer oil is starting to leak from crack... | Loss of insulating oil will result in transformer damage, increased maintenance costs and plant downtime. | Status October 2024: Open. Status quo remains. Note: It has been noted that transformer oil leaks seem to have increased after changing over to Ester type oil. | Open | M Bester | Monitoring, no serious leaks detected
| P56 | Electrical | Gloria vent fans transformer 70EP55TF04 | Transformer oil leaking from transformer... | Loss of insulating oil will result in transformer damage, increased maintenance costs and plant downtime. | Status October 2024: Completed. Leak repaired. | Completed
| P57 | Electrical | Main stores | 1. Electric motors not included in motor turning register... 2. Transformer is not being stored in bunded area... 3. Spare motor (460 kW) not on heating... Status October 2024. 1. Completed. 2. Completed. 3. Completed... | 1. Premature failure of spare motors... 2. Localised ground contamination. 3. Premature failure of critical spare... | Status October 2024. 1. Completed. 2. Completed. 3. Completed... | Completed
| P58 | Electrical | N3 UG silo bottom motor and gearbox | 1. Motor lubrication point not covered. 2. Gearbox oil leak... | 1. Potential for debris ingress into motor bearing... 2. Damage to gearbox resulting in increased maintenance costs... | Status October 2024: Open. Area not surveyed, it was reported that replacement gearbox is on site and ETA for installation is in Q1 2025. | Open | S Sease | Motor replaced
| P59 | Electrical | N3 UG workshop area diesel storage | Bulk diesel storage tanks do not appear to be correctly bonded and earthed... Electric motor not compliant for hazardous area electrical installation... | Not to standard, installation not compliant for hazardous areas (class 3-flammable liquids) resulting in an unsafe condition and a fire risk. | Status October 2024: Open. It was reported that this is scheduled to be done by service provider (TotalEnergies) in Q1 2025. | Open | S Sease | COC received from Total
| P60 | Mechanical | N3 UG 60 CV01 | 1. No rip detection installed on belt. 2. No online condition monitoring of motor or gearbox... | 1. Belt rip detection is seen as a proactive measure in reducing catastrophic failure of belts... 2. Delayed detection of fault condition resulting in unexpected equipment failure and down time. | Status October 2024. 1. Completed - RIP detection has been installed. 2. Open- it was reported that a new system... is being installed... ETA of end 2026 for mine wide conveyor belt systems | Open | S Sease | Rip detector installed. Online detection project halted
| P61 | Electrical | N2 electrical COC. including bulk diesel storage tanks. | Last CoC issued dated 17/03/2020 should be updated at least every two years for electrical installations in hazardous locations... | Out of date records. | Status October 2024: Open. It was reported that this is scheduled to be done by service provider (TotalEnergies) in Q1 2025. | Open | M Mteki | Not completed by Total
| P62 | Mechanical | Lifting equipment test certificates | Test certificates have no reference to SANAS accreditation... | Potential for compromised services from service providers. SANAS accreditation is a formal process... | Status October 2024: Open. Status quo remains. | Complete | X Petersen | Certificates Uploaded
| P63 | Electrical | Transformer oil analysis records | Many transformers with ""critical"" risk level indicated on registers... | Compromised transformer maintenance and safety. Transformer failures can also result in transformer fires. | Status October 2024: Open. Oil sampling was done in July 2024... however oil analysis summary report for October 2024 shows 20 transformers as ""critical"" condition for the mine that require attention. | Open | Engineers | Continuous process
| P64 | Mechanical | Oil analysis reports (plant equipment and TMM) | Issues and recommendations as noted in individual reports... | Premature wear and tear resulting in equipment breakdown and plant stoppage. | Status October 2024: Completed. A system (online for primary equipment) is in place. This is regarded as ongoing in line with business requirements. | Completed
| P65 | Structure / Buildings | NCHW 3 Underground Decline Area | At the bottom of the shaft, at the workers' platform, the plinth supporting the platform has spalling concrete... | The concrete strength is compromised and repairs are necessary. | Status Oct 2024: Open. Status quo, no changes - repair all damaged concrete plinths | Open | S Sease
| P66 | Structure / Buildings | NCHW 3 Underground Silo Bottom Substation MCC60 | The walls of the substation are cracked, and the cracks are substantial... | The cracks may grow bigger affecting structural stability. | Status Oct 2024: Open. Area not surveyed; however ongoing monitoring is in place. | Open | S Sease
| P67 | Structure / Buildings | NCHW 2 Sink 2 Plant Silo | The Seam 2 Silo has cracks. We are advised that an investigation is underway... | Integrity and stability of the silo may be affected. | Status Oct 2024: Open. Status quo, no changes on tender process. | Open | M Bester | Crack detectors installed on Silo's
| P68 | Structure / Buildings | Gloria Material Silo | The Main Decline Material Silo shows signs of moisture in several places... | Investigate and implement appropriate action as necessary. Tank possibly requires water proofing, lining, etc. | Status Oct 2024: Open. Status quo on tender process. | Open | M Bester | Crack detectors installed on Silo's
| P69 | Structure / Buildings | NCHW 2 & 3, Main Stores | Damage to concrete structures noted at various areas, which include concrete spalling on plinths, cone crusher tunnel and at the stores Afdak''... | Structure integrity. | Status October 2024: Completed. | Completed
| P70 | Structure / Buildings | Main Stores Afdak Store | Steel Plates are used instead of concrete grouting plinths to support the steel column... | Compromised structure integrity. | Status October 2024: Completed. | Completed
| P71 | Structure/ Buildings | Main Stores Afdak Store | Missing Bolts and Nuts at the Afdak Shelter... | Compromised structure integrity. | Status October 2024: Completed. | Completed
| P72 | Structures/ Buildings | NCH 2 & Loadout - conveyor supports / columns and Seam 1 Silo2 | No protection in place for conveyor belt support column/s and Seam 1 Silo 2 may be vulnerable to mechanical impact... | Unprotected supports / columns are susceptible to mechanical damage. | Status Oct 2024: Completed. | Completed
| P73 | Electrical | Gloria - ROM silo CV 25/ CV30 structure. | 1. Metal structure below concrete structure does not appear to be earthed. 2. CV 25/30 metal structure does not appear to be earthed... | Not to standard, potentially unsafe condition. | Status October 2024. 1. Open... 2. Completed... | Open | M Bester
| P74 | Electrical | All MCCS | Earth leakage circuit breakers are tested on a 6-month basis, however there is no visual indication displayed on the panel of these tests... | May result in earth leakage circuit breakers not being tested. | Status October 2024: Completed. The inspection register is in place; however no stickers will be placed on panels for visual indication of inspection and testing. | Completed
| P75 | Electrical | Various transformers | Transformers leaking oil at the following locations... | Loss of insulating oil will result in transformer damage, increased maintenance costs and plant downtime. | Status October 2024: Open. Most oil leaks have been repaired; however, leaks were noted at the following transformers. Gloria TR 60EP-40-TF15. NCH2 PS LOS MCC2, TR 50LE52 TF 12. NCH2 THS MCC 160EP 40BL 15. | Open | Engineers
| P76 | Electrical | Gloria - substation 90Y | Very low oil levels in TRs - 70EP10TF13 and 70EP10TF12. | Loss of insulating oil will result in transformer damage, increased maintenance costs and plant downtime. | Status October 2024: Completed. Oil level filled correctly, ongoing inspection and maintenance. | Completed
| P77 | Electrical | NCH 3- 60EP50 substation transformers | Transformers equipped with new type of silica gel for transformer conservator breathers... Transformer breathers showing green in colour at the time of survey... | Moisture entering transformers can result in damage to the transformers, increased maintenance costs and plant downtime. | Status October 2024: Completed. ...awareness has been done on 24 October 2024 as per records received. | Completed
| P78 | Electrical | NCH 3 bulk diesel storage installation | 1. Several flange jumpers are missing... 2. Earth proving device for tanker offloading seems to be defective... 3. No offloading procedure has been erected at tanker offloading point... | Compromised safety for electrostatic discharge in the presence of combustible liquid. | Status October 2024: Open. It was reported that this is scheduled to be done by service provider (TotalEnergies) in Q1 2025. | Open | M Mteki
| P79 | Electrical | Black Rock Main consumer genset transformers | 1. The current design of transformer conservators does not have sight glass level indication installed. 2. Signs of oil leaks on sides of transformers... | 1. Unable to visually confirm oil level inside conservators... 2. Loss of insulating oil will result in transformer damage... | Status October 2024. 1. Open area not surveyed. 2. Open area not surveyed. | Completed | M Mteki | It's sealed unit and pre-vaccumed
| P80 | Electrical | Belgravia 2MVA transformer | 1. Buchholz relay is installed but not electrically connected. 2. Low oil level in conservator. | 1. Compromised transformer safety. 2. Loss of insulating oil will result in transformer damage... | Status October 2024. 1. Completed - Buchholz relay is not connected... no plans to install switchgear. 2. Completed. | Completed
| P81 | Electrical | Gloria - vent fans substation | BTU battery levels low, close to minimum level. | Potential for compromised protection and tripping of circuit breakers. | Status October 2024: Completed. BTU levels correct at the time of survey. | Completed
| P82 | Safety | Main stores | No PPE signage erected on entrance gates to chemical storage area... | Potential exposure of employees to chemicals and potential contravention of OCCUPATIONAL HEALTH AND SAFETY ACT, 1993... | Status October 2024: Open. ...a new store has been constructed, however no PPE signage has been erected as yet. | Open | M Mteki | To be installed - Aug 2025
| P83 | Environmental | Main stores | Ensure that only transformers filled with biodegradable Ester Oil are stored outside of bunded areas. All transformers filled with Mineral Oil to be stored inside bunded areas. | Potential for environmental contamination from Mineral Oil leakage. | Status October 2024: Completed. Area not surveyed; however it was reported that transformers are filled with Ester Oil... | Completed
| P84 | Mechanical / safety | Gloria - UG workshops | 1. Several vehicles parked up with no stop blocks (wheel chocks) in place. 2. Roof bolter left standing supported on onboard hydraulic rams / jacks... | 1. Potential for vehicles to move in an uncontrolled manner... 2. Potentially unsafe condition should the onboard hydraulic ram seals fail... | Status October 2024: Completed. No deviations noted at the time of survey. | Completed
| P85 | Electrical / Safety | Gloria - UG boilermakers' workshop | 1. Welding machine with loose work cable connection at welding machine. 2. Power source for electric welding machines not locked out when welding machines are not in use. | 1. Not to standard resulting in electrical arching... 2. Not to standard resulting in potentially unsafe condition. | Status October 2024: Completed. New welding machine procured and included in an inspection register. | Completed
| P86 | Safety | Gloria - UG mechanical & electrical workshop | Work being conducted on articulated vehicle with the following hazards noted. 1. Articulation lockout bar not engaged... 2. Not all lockout tags calipers engaged... 3. Portable electric tools not included in a portable electric tool inspection register... | 1. Not to standard resulting in unsafe condition... 2. Not to standard resulting in unsafe condition... 3. Not to standard, potentially unsafe. | Status October 2024. All completed. | Completed
| P87 | Electrical | Gloria - UG electrical workshop | 1. Portable electric tools not included in a portable electric tool inspection register. 2. DB board - very hot connection... | 1. Not to standard, potentially unsafe. 2. Not to standard, potentially unsafe. | Status October 2024. 1. Completed... 2. Open thermal scan of DB at the time of survey still indicates hot surfaces and should be changed out. | Open | S Dubazane
| P88 | Safety | Gloria - UG, close to 98Y substation | Compressed gas bottles secured to flexible plastic pipe. | Not to standard, potentially unsafe condition. | Status October 2024: Completed. Gas bottles have been removed. | Completed
| P89 | Mechanical | Gloria - UG, new apron feeder for CV78 | 1. Hydraulic system for apron hopper is not operational... 2. Hard chrome section of hydraulic ram is not covered... | 1. Not to standard, equipment not operating as designed, may be unsafe. 2. Damage to hydraulic seals/system due to corrosion pitting... | Status October 2024: Completed. All issues resolved. It was advised that CV78 is to be decommissioned in due course. | Completed
| P90 | Mechanical | Gloria - UG, new conveyor (CV78) | Turnbuckles used for conveyor support to be confirmed suitable for the intended load. | Potential for conveyor collapse due to turnbuckle failure. | Status October 2024: Completed. It was stated that this has been confirmed to be suitable for the intended load. | Completed
| P91 | Mechanical | Gloria - UG, new conveyor (CV78), close to apron feeder | 1. Bearings for roller at position 20 have completely collapsed... 2. Bearings for roller at position 40 have seized... | Impact on conveyor belt operation and also a potential fire risk due to friction between moving belt and stationary rollers. | Status October 2024: Completed. Planned maintenance system requires regular inspection... | Completed
| P92 | Structure / Buildings | Gloria Underground (UG) Main Decline Conveyor | The main decline conveyor shares a pathway with mining vehicles (TMM's, LDV). The conveyor is not protected from vehicles and is exposed to incidental impact. | Unprotected supports / columns are susceptible to mechanical damage from the vehicle impact. | Status October 2024: Open. Outstanding. Traffic control signalling is installed... | Open | S Dubazane | Due to constraints, decided that current control is sufficient
| P93 | Structure / Buildings | Gloria UG Electrical Workshop | The brick wall at the electrical workshop is cracked... | The cracks should be monitored. | Status October 2024: Completed. No additional cracks are developing on the wall and the existing crack is monitored. | Completed
| P94 | Structure / Buildings | Gloria UG High Breed Silo | Bottom of High Breed Silo is corroded. | Corrosion may compromise the strength and stability of the silo. | Status October 2024: Completed. The silo has been sandblasted and repainted. | Completed
| P95 | Structure / Buildings | Gloria UG - CV-78-0028 | The concrete plinth supporting the conveyor at idler CV-78-0028 is spalled, concrete is damaged at the edges. | Damaged concrete exposes reinforcement bars. | Status October 2024: Open. Status quo. | Open | S Dubazane
| P96 | Structure / Buildings | Gloria Wet Screening Plant | The screen plant structural steel frame and supporting columns are not protected from vehicle impact. | Unprotected supports / columns are susceptible to mechanical damage from the vehicles. | Status October 2024: Completed. New Jersey barriers are installed. | Completed
| P97 | Structure / Buildings | Gloria Main Ventilation Fans | Reinforcement bars are exposed and rusted in the concrete beams supporting the ventilation fans. | Damaged concrete exposes reinforcement bars. | Status Octpber 2024: Open. Status quo more reinforcement is exposed and corroded. | Closed | X Petersen
| P98 | Structure / Buildings | NCHW 2 Seam 1 Wet Screening Plant | Roof sheeting has come loose. | Loose roof sheeting is exposed to further wind damage. | Status October 2024: Completed. | Completed
| P99 | Structure / Buildings | NCHW 3 Fuel Depot / Diesel Bay | There are several cracks forming on the expansion joint along the bund wall. | Depth of cracks should be assessed and repaired if necessary. | Status October 2024: Completed. Area not surveyed closed subject to confirmation in the next audit. | Completed
| P100 | Structure / Buildings | Water Reservoirs | There are minor cracks on some of the reservoirs. These should be monitored and if they excessive repairment measures should be implemented. | These should be monitored and if they excessive repairment measures should be implemented. | Status Oct 2024: Open. Status quo on tender process | Open | M Bester | Cracks being monitored, new structural audit Dec 2025
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Itireleng provided calculations that shows the installation is within reasonable position
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Extra earth bonding done by African Fuel
Note on H15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wired on the Generator safety circuit
Note on H37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Open, the COCs will be done once the new FMS is installed
Note on H38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incorrectly located to my name
Note on H45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Within the Bunded Area, placed the order with TFS to repair
Note on H79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COC Done for Nchw3
Note on H80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: it's sealed unit and pre-vaccumed

## New
Category | Item | Discipline | Location | Observation | Consequence | Status comment | Current Status | Responsible person | Update Aug 2025 | Photos
Mining, TSF, SHERQ, Clinic & Security | N1 | Mining | Gloria Shaft, 74 N Section | Drill Rig operator marked all in order, but the onboard fire suppression system needed to be maintained. | Onboard fire suppression system might not operate during a fire. | Open |  | S Dubazane | Managed daily by pre-chack and planned maintenance
| N2 | Mining | Gloria Shaft, 74 N Section | Lifter plugs not used at 120N/124W, after face preparations and face marked - ready for drilling. | Non-compliance to legal and other requirements. Drilling into misfire resulting in an uncontrolled explosion. | Open |  | S Dubazane
| N3 | Mining | Gloria Shaft, 74 N Section | Large slips at 120N/124W sidewall unsupported, M/O said they use scaler to bar it down. | Potential FOG's. | Open |  | S Dubazane
Fire Protection | N4 | Sprinkler and deluge installation control valves (ICV) | Mine wide | Pressure valves on ICV's are regularly damaged during winter months due to freezing temperatures. Consider gauges specifically designed for low temperatures or cover gauges with insulated covers. | Cost savings. | Open |  | Itirelelng | Supply Heavy Duty Deluge Covers in Progress - Quotations sent to End Users awaiting approvals
| N5 | Gas suppression | Gloria 10Y substation | Pyroshield discharge hoses are showing signs of degradation. NFPA 2001 (Standard on Clean Agent Fire Extinguishing Systems) provides guidance on the maintenance of flexible hoses... | Regular replacement and inspections are critical to ensure the effectiveness and safety of the suppression system... | Open |  | Itirelelng | Replacement of Hoses in Progress
| N6 | Fire Suppression | Gloria 10Y substation 70 EP 86 TRF01 | One of the high velocity water spray nozzles is out of alignment. | Failure of protection to operate as intended. | Open |  | Itirelelng | Completed
| N7 | Fire Suppression | Gloria 90Y Substation | Gloria 90Y consists of 3 separate rooms each fitted with individual Pyroshield suppression systems. All 3 rooms communicate via the rack room. Either isolate each of the communicating rooms... or interlock the three suppression systems to operate simultaneously. Conduct room integrity tests... | Fire extinguishing systems may not work as intended in the event that the room integrity is compromised... | Open |  | Itirelelng | Substation Interlocked
| N8 | Deluge | Gloria 90Y Substation, transformer 22/11 kV | One of the sprinkler spray heads has a slight water leak. | Fire system maintenance and inspection. | Open |  | Itirelelng | Completed
| N9 | Fire Suppression | NCH 2 LOS MCC2 | Conduct room integrity tests to ensure gas concentration is achieved and maintained for the period of time required by the design specifications. | Fire extinguishing systems may not work as intended in the event that the room integrity is compromised... | Open |  | Itirelelng | Room Integrity Test Done and Passed 13 November 2024
| N10 | Fire Pump | NCH2 Pump House | The diesel drive fire pump packing gland is leaking excessively. This should be attended to. | Pump performance. | Open |  | Itirelelng | Gland Packing adjusted during annual service
Engineering | N11 | Mechanical | Gloria CV 25 | Deflecting rollers near silo very noisy. | Impact on conveyor belt operation and also a potential fire risk due to friction between moving belt and stationary rollers should deflecting rollers seize in place. | Open |  | M Bester
| N12 | Electrical | Site wide | Inhouse bonding and earthing tests are done using inhouse equipment. It could not be established if equipment used has been tested and calibrated by a recognised testing house (SANAS accredited). | Potential for incorrect test results and not traceable reference sources, resulting in compromised testing of installation. | Open |  | G Karsten | SANAS to be confirmed on testing
| N13 | Electrical | 10Y MV substation | BTU batteries with acid buildup showing on batteries. | Potential for compromised protection and tripping of circuit breakers. | Open |  | M Bester | Completed
| N14 | Electrical | MCC 101Y & 102Y | Aircon unit (70EP-87PA16) for MCC room had tripped out and MCC was noticeably warm. Aircon unit monitoring is not connected to SCADA. | Reduced lifespan of electrical equipment. | Open |  | M Bester | Completed
| N15 | Electrical | Gloria 90Y | BTU battery levels at the minimum level. | Potential for compromised protection and tripping of circuit breakers. | Open |  | M Bester | Completed
| N16 | Electrical | Gloria UG 96Y | 500 KVA transformer with no Buchholz relay in place. | Compromised transformer safety. | Open |  | S Dubazane | Completed
| N17 | Mechanical | Gloria UG belt 52H take up tower. | No formal scheduled inspection of belt strike. | Potential for belt to malfunction. | Open |  | S Dubazane | Completed
| N18 | Electrical | Site transformers | For transformer oil testing, consider the merits of using graphical methods for the identification of faults in power transformers. | Improved critical asset care. | Open |  | G Karsten | Migtating to new reporting system. Will be incorporated in Power BI reports. June 2026
| N19 | Mechanical | Site | 1. Pressure vessel inspection and test certification as issued by service provider JV Specialized Services does not show reference to SANAS accreditation. 2. NDT inspection and test certification as issued by service provider Owen Masterton does not show reference to SANAS accreditation. | Possible compromised service from 3rd party service providers. | Open |  | G Karsten
| N20 | Structures / Buildings | Gloria 101/102Y Thickener MCC Substation | The structures (thickener, conveyor) near the substation which are not protected from impact collision by plant mobile vehicles and bakkies. | The structures are directly exposed to impact collision. | Open |  | M Bester | Completed
| N21 | Structures / Buildings | Gloria Underground TMM Workshop | There is an old disused extractor ventilation fan hanging over the maintenance bay near the plant tearoom. | Obstructive and limits working space. This should be dismantled and removed. | Open |  | S Dubazane
| N22 | Structures / Buildings | Gloria Underground TMM Workshop | 1. Waste or Water Drainage covered with steel grating is not aligned in order to transfer smoothly to the next drain. 2. Debris is trapped in the drainage and blocks the drain. | 1. The overflow runs onto the maintenance floor instead of into the drainage channel. 2. This condition clogs the drainage channel. | Open |  | S Dubazane | Completed
| N23 | Structures / Buildings | Gloria Underground TMM Workshop | The electrical cables penetrating the wall inside the diesel & oil storage area compromises the stability of the wall/s. | Cable penetrations should be done properly so as not to interfere with the integrity of the walls. Implement repairs to stabilize the wall/s. | Open |  | S Dubazane
| N24 | Structures / Buildings | Gloria Underground Bottom of CV54 | There are signs of corrosion at the bottom of the material bin at CV54. | The extent of the corrosion should be investigated, and if necessary. repair work should be implemented to protect the structure from further corrosion. | Open |  | S Dubazane | Belt not in use anymore
| N25 | Structures / Buildings | Gloria Underground High Grade Silo | Power pack for transfer belt for high grade silo is protruding into the service way for mobile equipment, including LDVs. | The power pack is directly exposed to impact damage. Consider providing a barrier to protect this equipment. | Open |  | S Dubazane
| N26 | Structures / Buildings | Gloria Underground - CV78 below crusher | The liners at the bottom of the crusher are damage. | There is excessive material spillage. | Open |  | S Dubazane
| N27 | Structures /Buildings | Gloria Underground - CV 75 Portal Decline | The surface shaft entrance into the decline has substantial cracks. | Compromised structure with possible structure failure. Investigate the extent of the cracks, seek advice from a structural engineering company. | Open |  | S Dubazane
| N28 | Structures / Buildings | Main Stores - Blink Store | The "I" section beam supporting the frame over the door entrance has been impacted and is bent. | The IBR sheeting is therefore loose and is not fixed to the building frame due to the bent beam. | Open |  | M Mteki
| N29 | Structures / Buildings | Main Stores Cement Store | Deteriorated sisalation is loose and hanging close to light fittings and the sprinkler system. | The deteriorated sisalation is exposed and also increases the fire load as well as possibly compromising the efficiency of the sisalation. | Open |  | M Mteki