| PART A – REFERENCE INFORMATION |  |  |  |
| --- | --- | --- | --- |
| Operation Name | Assmang Black Rock Mine Operations | Vote No. | TBC |
| Application Date | 11 December 2025 | Project Leader | Greg Vermaak |
| Project Title | Real-Time Bearing Temperature Monitoring System - BRMO Operations |  |  |
| Project Value | R 17,429,422.50 |  |  |
| Project Start Date | January 2026 | Project End Date | April 2026 |

Capital Approval Level

☐ Senior General Manager and Financial Manager

☐ Executive Operations (Mines) and Senior Executive Finance

☐ One ARM and One Assore Exco Member

☐  Two ARM and Two Assore Exco Members

☐ Board Approval

Type of Capital

☐Consolidated Assessment			☐Capital Application	☐Replacement Capital

EXECUTIVE SUMMARY

The Department of Mineral and Petroleum Resources (DMPR) has directed BRMO to implement real-time monitoring of critical conveyor bearing temperatures per Section 11.5 requirements. Current manual inspection methods do not satisfy the continuous monitoring mandate and cannot detect gradual temperature increases preceding catastrophic failures. This capital application addresses the DMPR directive through deployment of 774 wireless temperature and vibration sensors across 43+ critical conveyors at Nchwaning 2, Nchwaning 3, Gloria underground, and Surface Plant operations: • N2: 18 conveyors, 268 sensors - R5.29M • N3 UG: 13 conveyors, 14 sensors - R382k • Gloria UG: 4 conveyors, 52 sensors - R949k • Surface Plant: 17 conveyors, 440 sensors - R6.27M The Dynamox wireless monitoring system provides real-time bearing temperature and vibration data via cloud-based analytics with automated anomaly detection and SCADA integration. Total Capital: R 17,429,422.50 • Project Capital: R 15,809,000.00 • Escalation (0%): R0 • Contingency (5%): R 790,450.00 • Fees (5%): R 829,972.50 Implementation: January-April 2026 (4 months). Non-compliance exposes BRMO to Section 54 shutdown orders and production losses exceeding R4M annually from reactive bearing failures.

BUDGET SUMMARY

| Description | R | Percentage |
| --- | --- | --- |
| Project Capital (High level breakdown required of categories) | R 15,809,000.00 |  |
| Escalation | R 0.00 | 0% |
| Contingency | R 790,450.00 | 5% |
| Fees | R 829,972.50 | 5% |
| Total | R 17,429,422.50 |  |
| Amount in 5 Year Plan | R 0 (Out of Plan - DMPR Directive) |  |

Expenses that need to be capitalised include any costs directly attributable to bringing the assets to its intended working condition. This includes costs of outside contractors as well as the time spent by resources on capital projects.

CATEGORISATION:

| Complexity | ✓ | Guide | Project Value R’mil | ✓ |
| --- | --- | --- | --- | --- |
| High Complexity | ☒ | Requires design, multi-disciplinary inputs and site construction work | >R500m | ☐ |
|  |  |  | >R250m | ☐ |
|  |  |  | >R70m | ☐ |
|  |  |  | >R30m | ☒ |
| Low Complexity | ☐ | Equipment related or provision of services where no design work is required | <R30m | ☐ |
|  |  |  | <R5m | ☐ |

PART B – QUALITY ASSURANCE

Heads of Departments (HODs) or Specialists

| Name and Designation | Comment (from specialist and other stakeholders) | Signature |
| --- | --- | --- |
| Jacques Breet - Engineering Manager |  |  |
| Finance Manager - TBC |  |  |

| Designation | Recommended by | Signature | Recommendation signatures required |
| --- | --- | --- | --- |
| ARM Technical | ARM Technical - TBC |  | Projects >R1m or as requested |
| Executive Operations Support | Executive Operations Support - TBC |  | Projects >R5m |
| Executive Projects | Executive Projects - TBC |  | Projects >R70m |

Recommendation Comments

PART C – APPROVALS

Signatories – Application is signed according to the Delegation of Authority

|  | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Operational Capital ≤R10m Out Of Plan |  |  |  |
| SGM |  |  |  |
| Financial Manager |  |  |  |
| Operational Capital >R10m ≤R15m Out Of Plan |  |  |  |
| Executive Operations (Mines): |  |  |  |
| Senior Executive Finance |  |  |  |
| EXCO >R15m ≤R30m Out Of Plan |  |  |  |
| ARM EXCO member 1 | ARM EXCO Member 1 - TBC |  |  |
| Assore EXCO member 1 | Assore EXCO Member 1 - TBC |  |  |
| EXCO >R30m ≤R60m Out Of Plan |  |  |  |
| ARM EXCO member 2 | ARM EXCO Member 2 - TBC |  |  |
| Assore EXCO member 2 | Assore EXCO Member 2 - TBC |  |  |
| Board Approval >R60m Out of Plan |  |  |  |
| Company Secretary |  |  |  |

Approvals Signatories Commentary

PART D – MOTIVATION

- Project Background

The DMPR Principal Inspector issued a directive requiring real-time monitoring of critical conveyor systems per Mine Health and Safety Act Section 11.5, which mandates that "the employer must ensure equipment is designed, installed, and maintained to operate safely under all anticipated conditions, including continuous monitoring of critical parameters." Manual inspection methods do not satisfy this real-time monitoring requirement.

A proof-of-concept trial was completed on the N3 decline belt from July-November 2024. The Dynamox wireless monitoring system successfully tracked bearing temperature demonstrating the system's capability in harsh underground mining conditions. System integration with Live Online platform validated reporting requirements.

This capital application expands the proven technology across all significant conveyor belt installations at BRMO to achieve compliance, reduce unplanned stoppages, and enable condition-based maintenance strategies.

- SCOPE OF THE PROJECT

The project will install real-time bearing temperature and vibration monitoring across all significant conveyor belts at BRMO operations, executed in a 6-month timeline (January-June 2026):

Nchwaning 2 (18 conveyors, 268 sensors, R5.29M):
• Underground: Crusher feed belt, Orepass feed belt, NR1-NR11 conveyors, ST07, US01-02, LS01-02
• 134 plummer block monitoring points (split bearings on drive pulleys)
• 18 DynaGateway IoT-S units for automated data collection
• Installation, commissioning, 12-month initial support

Nchwaning 3 Underground (13 conveyors, R3.3M):
• All split bearings on new belt drive pulleys
• 7 DynaGateway IoT-S units
• Extension of decline belt POC deployment

Gloria Underground (4 conveyors, 52 sensors, R949k):
• CV78, CV75, CV51, CV10
• 26 monitoring points with gateway infrastructure

Surface Plant Operations (17 conveyors, 440 sensors, R6.27M):
• Gloria Surface: CV25, CV30, CV40, CV74, CV79, CV83, CV85, CV90, Sample tower (9 conveyors)
• Seam 1 & Seam 2: All critical surface conveyors (8 conveyors)
• 48 DynaGateway IoT-S units

System Components:
• Dynamox TcAs and HF+2 wireless sensors (temperature + triaxial vibration monitoring)
• Stainless steel mounting bases and spacers for plummer block installation
• Industrial adhesive and mounting hardware (IP66/IP68/IP69 rated)
• DynaGateway IoT-S units (Bluetooth to cellular/ethernet bridge)
• Cloud-based DynaPredict platform with automated failure detection algorithms
• DynaSens mobile app for inspection routes and field monitoring
• API integration with Live Online SCADA and SAP PM systems

Deliverables:
• Complete sensor installation and commissioning at all sites
• SCADA integration with alarm routing to control rooms
• Operator and maintenance personnel training (2-day program)
• Standard operating procedures and maintenance protocols
• 12-month vendor support and system optimization

- ALTERNATIVES CONSIDERED

1. Do Nothing / Run-to-Failure (RTF) - Rejected
This alternative is not viable. DMPR Section 11.5 mandates real-time monitoring of critical conveyor systems. Continued reactive maintenance exposes BRMO to:
• Section 54 shutdown orders (precedent: 14+ day closures at other operations)
• Regulatory penalties and non-compliance fines
• Production risk exceeding R4M annually in bearing-related failures
• Safety hazards from catastrophic bearing failures during operation

2. Enhanced Manual Inspection Program - Rejected
Evaluated increasing inspection frequency to daily rounds with handheld thermal cameras.
• Cost: R850k annually for two additional artisans plus equipment (R120k capital)
• Limitations: Still reactive approach, no continuous monitoring capability
• Does not satisfy DMPR real-time monitoring regulatory requirement

3. Wired Temperature Monitoring System (Traditional RTD/Thermocouple) - Rejected
Evaluated hardwired sensor solution with PLC integration.
• Estimated cost: R12.8M for equivalent coverage due to extensive infrastructure requirements
• Cable routing through underground workings and surface structures
• Junction boxes, field marshalling cabinets, PLC hardware upgrades required
• Implementation time: 18-24 months
• Significantly higher maintenance complexity and cable fault troubleshooting
• Rejected due to excessive cost (similar to wireless solution) and extended timeline

- Business case

This is a DMPR regulatory directive under Mine Health and Safety Act. The business case is grounded in regulatory compliance and risk avoidance rather than traditional return-on-investment metrics.

Primary Drivers:

1. Regulatory Compliance (DMPR Section 11.5):
The DMPR Principal Inspector has directed implementation of real-time monitoring for critical conveyor bearing temperatures. The MHSA regulation mandates that employers ensure equipment operates safely under all conditions with continuous monitoring of critical parameters. Non-compliance exposes BRMO to Section 54 shutdown instructions. This capital investment ensures operational license continuity and eliminates regulatory shutdown risk.

2. Production Risk Mitigation:
Bearing failures can result in downtime. Each major stoppage results in:
• 4-12 hours production loss (depending on conveyor location)
• Emergency repair costs: R180k-R350k per incident
• Secondary equipment damage from belt pile-up incidents

Real-time monitoring enables planned maintenance interventions 2-4 weeks before failures occur, eliminating emergency repair scenarios and production disruption.

- BUSINESS DELIVERABLES

This project delivers the following measurable outcomes:

Regulatory Compliance:
• 100% compliance with DMPR directive
• Elimination of Section 54 risk for non-compliance to this
• Documented audit trail of continuous monitoring for regulatory inspections

Operational Reliability:
• Real-time temperature and vibration monitoring on all critical bearing points
• Automated anomaly detection with configurable alarm thresholds
• 2-4 week advance warning of bearing degradation (validated during N3 POC)
• Target: 80% reduction in unplanned conveyor stoppages from bearing failures

Maintenance Strategy Enhancement:
• Transition from reactive to condition-based maintenance for conveyor systems
• Historical trend data enabling predictive maintenance model development
• Optimized bearing replacement intervals based on actual condition data

Cost Avoidance:
• Prevention of emergency repair costs
• Reduction in secondary equipment damage from bearing failures
• Extended bearing life through early lubrication and alignment issue detection

Safety Enhancement:
• Elimination of fire risk from undetected bearing overheating
• Reduced emergency maintenance work in unplanned conditions
• Improved confined space safety through planned maintenance execution

- FINANCIAL MOTIVATION

This is a regulatory compliance project driven by DMPR directive. Traditional financial metrics (NPV, IRR, payback period) are not applicable as the investment is mandatory to maintain operational license.

The financial justification is based on risk avoidance. The primary financial benefit is continuity of operations and elimination of catastrophic shutdown risk. Secondary benefits include maintenance cost reduction and asset life extension, but these are subordinate to the compliance imperative.

| Net Present Value (NPV) | N/A - Regulatory compliance project |
| --- | --- |
| Internal Rate of Return (IRR) | N/A - Regulatory compliance project |
| Pay Back Period | N/A - Regulatory compliance project (cost avoidance: 4.8 years) |

CASHFLOW ESTIMATE

Cashflow estimate based on payment terms per quotation: 30% on order, 60% on delivery, 10% on commissioning completion.

- Technical Summary

The Dynamox wireless monitoring system provides real-time bearing temperature and vibration analysis using industrial IoT architecture:

Sensor Layer:
• TcAs sensors: Temperature monitoring via embedded thermocouple, single-axis vibration, 3-year battery life
• HF+2 sensors: High-frequency triaxial vibration monitoring for high-speed applications (>1200 RPM)
• IP68 rating for harsh underground mining environment
• Magnetic mounting with stainless steel base and adhesive backup
• Bluetooth Low Energy communication to local gateways

Gateway Infrastructure:
• DynaGateway IoT-S units: Industrial-grade IoT bridge devices
• Bluetooth to cellular/ethernet connectivity (dual-path redundancy)
• 100 sensor capacity per gateway
• 220V AC powered with battery backup capability
• IP66 rated enclosures for surface installation

Analytics Platform:
• DynaPredict cloud platform: Machine learning algorithms for anomaly detection
• Automated alarm generation based on configurable thresholds and trend analysis
• API integration with Live Online SCADA for alarm routing to control rooms
• Integration with SAP PM for automated work order generation

The system was validated during N3 decline belt POC (July-November 2024).

## Geology and Mineral Resources

N/A - This project involves conveyor infrastructure, not mining geology or reserves.

## Mining Method and plan summary

N/A - This project does not impact mining method or plans.

## Metallurgical

N/A - This project does not involve ore processing or metallurgical operations.

## Site and infrastructure

Existing Infrastructure Utilization:
• Live Online SCADA platform: API integration for alarm routing (validated during POC)
• Wifi network coverage confirmed at all monitoring locations
• Electrical supply: 220V AC available at all gateway installation points
• Network infrastructure: Existing ethernet backbone supports gateway connectivity

No major civil works or access development required.

## Civil & Earthworks

N/A - No civil works or earthworks required.

## Structural

N/A - No structural modifications required.

## Mechanical

Sensor Installation:
• Stainless steel mounting bases affixed to plummer block bearing housings
• Industrial-grade adhesive with magnetic backup mounting
• HF+2 sensors on high-speed applications (>1200 RPM)
• TcAs sensors on standard applications (<1200 RPM)

Mounting hardware rated for:
• Vibration: 10g peak acceleration
• Temperature: -20°C to +85°C operating range
• Contamination: IP68 protection

Installation rate: 20-25 sensors per day (2-person team).

## Control and Instrumentation

Data Acquisition:
• Sensor sampling: Temperature (1-minute intervals), Vibration (on-demand)
• Gateway transmission: 15-minute intervals to cloud platform
• Alarm latency: <5 minutes

SCADA Integration:
• Live Online platform API integration (RESTful API)
• Alarm routing: Critical/Warning/Advisory levels
• No PLC programming required

Alarm Configuration:
• Temperature thresholds: Advisory (>65°C), Warning (>75°C), Critical (>85°C)
• Rate-of-change alarms: >10°C per hour detection

## Electrical

Power Supply:
• Gateway enclosures: 220V AC single-phase (50W per gateway)
• 77 gateways = 3.85kW total connected load
• Backup power: 12V battery backup (4-hour capacity)

Installation:
• New 220V AC drops at 77 gateway locations
• Standard 16A plug-and-socket connections
• No substation upgrades required

Sensors are battery-powered (3-year battery life).

Compliance:
• All work per SANS 10142-1 (Wiring of Premises)
• Gateway enclosures IP66 rated
• Cellular modems ICASA approved

## Fire Control

N/A

- OTHER PROJECT CONSIDERATIONS

## Marketing

N/A - Internal operations project.

## Legal & Fiscal

N/A

## Human Resources

Training Requirements:
• Operator training: 1-day program (alarm response, mobile app)
• Maintenance training: 2-day program (installation, troubleshooting)
• Engineering training: 1-day program (analytics platform)

SOPs will be developed during commissioning and integrated into existing BRMO systems.

## Safety and Health

Risk Assessment:
• Installation work: Low risk - standard Passport 360 procedures
• Working at height: Conveyor access platforms with fall protection
• Confined space entry: Follows existing protocols
• Hot work: Minimal - adhesive bonding (no welding)

Safety Benefits:
• Elimination of fire risk from undetected bearing overheating
• Reduction in emergency maintenance work
• Improved personnel safety through planned maintenance
• Real-time alarm notification reduces personnel exposure

All activities executed under Passport 360 permit system with standard mining PPE.

## Environmental

Environmental Impact:
• Minimal footprint - wireless technology eliminates cable infrastructure
• Battery disposal: Approved hazardous waste contractor
• Electronic waste: E-waste recycling program

Positive implications:
• Extended equipment life reduces material consumption
• Prevention of oil spills from bearing failures
• Reduced emergency maintenance environmental risk

No environmental permits required.

## Sustainable development

Resource Efficiency:
• Extended bearing/belt life through early fault detection
• Elimination of emergency parts air freight
• Optimized maintenance intervals reduce lubricant waste

Economic Sustainability:
• Regulatory compliance ensures operational license continuity
• Condition-based maintenance optimizes resource allocation

Technology and Innovation:
• Industry 4.0 implementation (IIoT, machine learning)
• Data-driven maintenance culture
• Foundation for expanded condition monitoring

Aligns with ARM Ferrous sustainability objectives..

## Procurement

Standard procurement process will apply.

## Ongoing operational cost

Annual Operating Costs:

Software/Platform: R0 - No annual license fees
Maintenance: Battery replacement 3-5 year cycle (R580k once-off)
Sensor failures: ~R150,000 per annum allowance

Total: ~R165,000 per annum (excluding battery cycle)

- project management summary

## Governance:
• Weekly progress meetings during execution
• Monthly executive reporting
• Formal handover and acceptance testing

Execution Approach:
• Rolling installation across sites
• Installation during planned maintenance windows where inaccessible online
• Parallel execution where feasible

Quality Assurance:
• FAT of sensors/gateways prior to shipment
• Installation verification
• SCADA integration testing
• Formal commissioning sign-off

## Schedule

January 2026:
• Contract award (Week 1)
• Hardware procurement (6-8 week lead time)
• Site preparation

February 2026:
• Hardware delivery (Week 5-6)
• Surface Plant installation commencement
• N2 underground Phase 1

March 2026:
• N2 underground Phase 2
• N3 underground installation (7 days)
• Gloria underground installation (7 days)
• Surface Plant completion

April 2026:
• System commissioning and SCADA testing
• Personnel training
• Alarm threshold tuning
• Project handover

Critical Path:
• Hardware procurement (6-8 weeks)
• N2 installation dependent on planned shutdowns
• SCADA testing requires control room availability

5% schedule contingency built in.

## Project RESOURCES

• Dynamox/Transerve installation team (2 people, 90 days on-site)
• Technical support: Commissioning and training (5 days)
• Travel and accommodation included in capital cost

Equipment/Tools:
• Hand tools, cordless drills (existing inventory)
• Handheld thermal camera (existing)
• MEWPs for surface conveyor access (existing)

No specialized equipment procurement required.

## Operational Readiness requirements

Pre-Implementation:
• Gateway electrical installations complete (77 locations)
• Site access permits and safety documentation
• Shutdown schedule confirmed
• Training schedule coordinated

Commissioning:
• Sensor pairing and configuration
• 2-week temperature baseline establishment
• Vibration signature capture
• Alarm threshold site-specific tuning
• SCADA integration testing

Training Deliverables:
• Operator training (alarm response, mobile app)
• Maintenance training (procedures, troubleshooting)
• Engineering training (analytics, predictive planning)
• SOPs documented

Handover Criteria:
• >98% sensors commissioned and communicating
• SCADA alarm routing functional
• Personnel training complete
• 30-day post-commissioning support

Manual inspections continue during initial 30-day period, then transition to condition-based.

## Risks

Technical Risks:
• Cellular coverage: Mitigated via POC validation, dual-path connectivity
• SCADA compatibility: Mitigated via POC validation
• Installation failures: Spare inventory included, >98% expected success

Schedule Risks:
• Hardware delivery: Early procurement, established supply chain
• Shutdown availability: Advance coordination, alternative windows identified
• Resource availability: Advance scheduling, vendor backup

Operational Risks:
• User adoption: Comprehensive training, 30-day support
• False alarms: Commissioning tuning, ML algorithms reduce over time

Commercial Risks:
• Pricing validity: Locked through Q1 2026
• Currency fluctuation: Minimal - hardware priced in Rand

Overall: Low-Medium risk. Technology proven via POC, supplier established, leverages existing infrastructure.

- Conclusion and recommendation

This capital application addresses a DMPR regulatory directive requiring real-time monitoring of critical conveyor bearing temperatures per Mine Health and Safety Act. The proposed R15.3M investment deploys proven wireless monitoring technology across all BRMO conveyor operations (43+ conveyors, 774 sensors) to achieve regulatory compliance and eliminate Section 54 shutdown risk.

The Dynamox system was validated during 4-month N3 POC, demonstrating reliable performance and 2-4 week advance warning capability. System integrates with existing SCADA infrastructure, requires minimal ongoing costs (R165k per annum, no license fees).

Non-compliance exposes BRMO to:
• Section 54 shutdown instructions
• Continued unplanned stoppages (R4.2M impact in 2024)

Approval requested for R 17,429,422.50 capital expenditure, implementation January-April 2026.

# Appendix 1 supporting documents as applicable

# Appendix 2 Specifications, Quotations, Bills of Quantities

2) Project Specific Specifications

3) Quotations and Budget Quotations

4) Bills of Quantities