## Jan 20 (hidden)
BURGER & Co.
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
| Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
| 2020-12-30 | 0 | 0 | 2019-12-31 | 0 | 0 | 2020-01-01 | 0 | 0 | 2020-01-02 | 0 | 0 | 2020-01-03 | 0 | 0 | 2020-01-04 | 0 | 0 | 2020-01-05 | 0 | 0 | 0 | 0
| 2020-01-06 | 0 | 0 | 2020-01-07 | 0 | 0 | 2020-01-08 | 0 | 0 | 2020-01-09 | 0 | 0 | 2020-01-10 | 0 | 0 | 2020-01-11 | 0 | 0 | 2020-01-12 | 0 | 0 | 0 | 0
| 2020-01-13 | 2 | 3 | 2020-01-14 | 2 | 3 | 2020-01-15 | 2 | 3 | 2020-01-16 | 2 | 1 | 2020-01-17 | 2 | 1 | 2020-01-18 | 2 | 1 | 2020-01-19 | 0 | 0 | 12 | 12
Conveyor O4-F (Mech) |  | 2 | 3 |  | 2 | 3 |  | 2 | 3 |  | 2 | 1 |  | 2 | 1 |  | 2 | 1
| 2020-01-20 | 2 | 0 | 2020-01-21 | 2 | 0 | 2020-01-22 | 2 | 1 | 2020-01-23 | 2 | 0 | 2020-01-24 | 0 | 0 | 2020-01-25 | 0 | 0 | 2020-01-26 | 0 | 0 | 8 | 1
Conveyor O4-F (Mech) |  | 2 | 0 | [7 empty] | 2 | 0 | Mine Pay Weekend | 0 | 0 | Mone Pay Weekend | 0 | 0 | Mine Pay Weekend
Conveyor O5-F (Struct) |  |  |  | No UV's | 2 | 0
Conveyor O6-F (Struct) | [7 empty] | 2 | 1
| 2020-01-27 | 2 | 1 | 2020-01-28 | 2 | 2 | 2020-01-29 | 2 | 1 | 2020-01-30 | 2 | 0 | 2020-01-31 | 2 | 0 | 2020-02-01 | 2 |  |  | 0 | 0 | 12 | 4
Conveyor O4-F (Mech |  | 2 | 1 |  | 2 | 2 |  | 2 | 1 |  |  |  | All constructions |  |  | All constructions |  |  | All constructions
Top of Tip 51-02 - Tip #2 (Struct) | [10 empty] | 2 | 0 | activities stopped | 2 | 0 | activities stopped | 2 | 0 | activities stopped

## Feb 20 (hidden)
BURGER & Co.
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
| Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
| 2020-02-03 | 0 | 0 | 2020-02-04 | 0 | 0 | 2020-02-05 | 0 | 0 | 2020-02-06 | 0 | 0 | 2020-02-07 | 0 | 0 | 2020-02-08 | 0 | 0 | 2020-02-09 | 0 | 0 | 0 | 0
| All constructions |  |  | All constructions |  |  | All constructions |  |  | Retraining on Revised |  |  | Retraining on Revised |  |  | Retraining on Revised
| activities stopped |  |  | activities stopped |  |  | activities stopped |  |  | Method Statements |  |  | Method Statements |  |  | Method Statements
| 2020-02-10 | 2 | 1 | 2020-02-11 | 2 | 0 | 2020-02-12 | 2 | 0 | 2020-02-13 | 4 | 0 | 2020-02-14 | 2 | 0 | 2020-02-15 | 2 | 0 | 2020-02-16 | 0 | 0 | 14 | 1
Conveyor O4-F (Mech) |  | 2 | 1 |  | 2 | 0 |  |  |  |  | 2 | 0 | Letter have been |  |  | Decline closed - Mine
Top of Tip 51-02 - Tip #1 (Struct) | [7 empty] | 2 | 0 |  | 2 | 0 | send out that all | 2 | 0 | Working in Decline | 2 | 0
4 UV's is on lockout
| 2020-02-17 | 2 | 0 | 2020-02-18 | 2 | 0 | 2020-02-19 | 2 | 0 | 2020-02-20 | 2 | 0 | 2020-02-21 | 2 | 0 | 2020-02-22 | 2 | 0 | 2020-02-23 | 0 | 0 | 12 | 0
Conveyor O4-F (Mech) | Decline Closed - Rain | 2 | 0 | Decline Closed - Rain | 2 | 0 | Decline Closed - Rain |  |  | Decline Opened
Top of Tip 51-02 - Tip #1 (Struct) | [7 empty] | 2 | 0 | at 08:00 | 2
Top of Tip 51-02 - Tip #2 (Struct) | [13 empty] | 2 |  |  | 2
| 2020-02-24 | 2 | 0 | 2020-02-25 | 2 | 0 | 2020-02-26 | 2 | 0 | 2020-02-27 | 2 | 0 | 2020-02-28 | 0 | 0 | 2020-02-29 | 0 | 0 | 2020-03-01 | 0 | 0 | 8 | 0
Conveyor O4-F (Mech) |  | 2 |  |  | 2 | [7 empty] | R&R |  |  | R&R |  | 0
Top of Tip 51-02 - Tip #1 (Struct) | [7 empty] | 2
Top of Tip 51-02 - Tip #2 (Struct) | [10 empty] | 2
Burger & Co. Site Manager:
Client Project Manager:

## Mar 20 (hidden)
BURGER & Co.
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
| Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
| 2020-03-02 | 0 | 0 | 2020-03-03 | 4 | 0 | 2020-03-04 | 4 | 1 | 2020-03-05 | 4 | 1 | 2020-03-06 | 4 | 1 | 2020-03-07 | 4 | 3 | 2020-03-08 | 0 | 0 | 20 | 6
Conveyor SF-01 | R&R |  |  | All UV's on break- | 1 | 0 | [11 empty] | 3
Top of Tip 51-02 - Tip #1 (Struct) |  |  |  | down | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0
Top of Tip 51-02 - Tip #2 (Struct) |  |  |  |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0
Conveyor 04-F |  |  |  |  | 1 | 0 |  |  | 1 |  |  | 1 |  |  | 1
Conveyor 05-F | [7 empty] | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  | 2 | 0
| 2020-03-09 | 1 | 1 | 2020-03-10 | 2 | 0 | 2020-03-11 | 2 | 1 | 2020-03-12 | 2 | 1 | 2020-03-13 | 2 | 1 | 2020-03-14 | 3 | 2 | 2020-03-15 | 0 | 0 | 12 | 6
Bulkhead #1 (Struct) |  |  |  |  | 1 | 0 | [10 empty] | 1
Bulkhead #2 (Struct) |  |  |  |  | 1 | 0 | [10 empty] | 1
Conveyor 04-F | [10 empty] | 2 | 0
North Crusher |  | 1 | 1 |  |  |  |  | 2 |  | Scalping Screen |  | 1 |  |  |  |  | 1
Conveyor SF-01 | [6 empty] | SF-01 WEBA H/Chute |  | 1 |  |  |  | SF-01 WEBA H/Chute | 2 | 1 | 2x Belts |  | 2
| 2020-03-16 | 2 | 0 | 2020-03-17 | 2 | 1 | 2020-03-18 | 2 | 1 | 2020-03-19 | 2 | 0 | 2020-03-20 | 2 | 0 | 2020-03-21 | 2 | 0 | 2020-03-22 | 0 | 0 | 12 | 2
Bulkhead #1 (Struct) | [13 empty] | 2
Bulkhead #2 (Struct) | [16 empty] | 2
Top of Tip 51-02 - Tip #1 (Struct) | [7 empty] | 2 | 0
Top of Tip 51-02 - Tip #2 (Struct) | [10 empty] | 2
Conveyor 04-F |  |  |  | Guards 04-F | 2 | 1 | Guards 04-F |  | 1
Conveyor 06-F |  | 2 | 0
| 2020-03-23 | 0 | 0 | 2020-03-24 | 0 | 0 | 2020-03-25 | 0 | 0 | 2020-03-26 | 0 | 0 | 2020-03-27 | 0 | 0 | 2020-03-28 | 0 | 0 | 2020-03-29 | 0 | 0 | 0 | 0
| 2020-03-30 | 0 | 0 | 2020-03-31 | 0 | 0 | 2020-04-01 | 0 | 0 | 2020-04-02 | 0 | 0 | 2020-04-03 | 0 | 0 | 1900-02-03 | 0 |  | 2020-06-03 | 0 | 0 | 0 | 0
Burger & Co. Site Manager:
Client Project Manager:

## Jun 20 (hidden)
BURGER & Co.
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
| Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
| 2020-06-01 | 0 | 0 | 2020-06-02 | 0 | 0 | 2020-06-03 | 0 | 0 | 2020-06-04 | 0 | 0 | 2020-06-05 | 0 | 0 | 2020-06-06 | 0 | 0 | 2020-06-07 | 0 | 0 | 0 | 0
| Medicals |  |  | Medicals |  |  | Medicals |  |  | Medicals |  |  | Medicals |  |  | Medicals |  |  | Off
| Inductions |  |  | Inductions |  |  | Inductions |  |  | Inductions |  |  | Inductions |  |  | Inductions
| Training |  |  | Training |  |  | Training |  |  | Training |  |  | Training |  |  | Training
| 2020-06-08 | 0 | 0 | 2020-06-09 | 0 | 0 | 2020-06-10 | 0 | 0 | 2020-06-11 | 0 | 0 | 2020-06-12 | 0 | 0 | 2020-06-13 | 0 | 0 | 2020-06-14 | 0 | 0 | 0 | 0
| Medicals |  |  | Medicals |  |  | Medicals |  |  | Medicals |  |  | Medicals |  |  | Medicals |  |  | Off
| Inductions |  |  | Inductions |  |  | Inductions |  |  | Inductions |  |  | Inductions |  |  | Inductions
| Training |  |  | Training |  |  | Training |  |  | Training |  |  | Training |  |  | Training
| 2020-06-15 | 4 | 0 | 2020-06-16 | 4 | 0 | 2020-06-17 | 4 | 0 | 2020-06-18 | 4 | 0 | 2020-06-19 | 4 | 0 | 2020-06-20 | 4 | 0 | 2020-06-21 | 0 | 0 | 24 | 0
Bulkhead #1 (Struct) |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  |  | 0
Bulkhead #2 (Struct) |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  | 2 | 0 |  |  | 0
0
0
0
| 2020-06-22 | 4 | 0 | 2020-06-23 | 4 | 0 | 2020-06-24 | 4 | 0 | 2020-06-25 | 4 | 0 | 2020-06-26 | 4 | 0 | 2020-06-27 | 4 | 0 | 2020-06-28 | 0 | 0 | 24 | 0
Bulkhead #1 (Struct) |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 |  |  | 1 | 0 |  |  | 0
Bulkhead #2 (Struct) |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 |  |  | 1 | 0 |  |  | 0
North Crusher |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 |  |  | 1 | 0 |  |  | 0
Top of Tip 51-02 - Tip #1 (Struct) |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 |  |  | 1 | 0 |  |  | 0
0
| 2020-06-29 | 5 | 0 | 2020-06-30 | 5 | 0 | 2020-07-01 | 5 | 0 | 2020-07-02 | 5 | 0 | 2020-07-03 | 5 | 0 | 1900-07-04 | 5 | 0 | 2020-06-05 | 0 | 0 | 30 | 0
Bulkhead #1 (Struct) |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  |  | 0
Bulkhead #2 (Struct) |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  |  | 0
North Crusher |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  |  | 0
Top of Tip 51-02 - Tip #1 (Struct) |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  |  | 0
Top of Tip 51-02 - Tip #2 (Struct) |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  | 1 | 0 |  |  | 0
Burger & Co. Site Manager:
Client Project Manager:

## Aug 20 (hidden)
Burger & Co 74 section Logistics
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
| Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
| 2020-07-27 | 2 | 0 | 2020-07-28 | 3 | 0 | 2020-07-29 | 3 | 0 | 2020-07-30 | 3 | 0 | 2020-07-31 | 3 | 0 | 2020-08-01 | 2 | 0 | 2020-08-02 | 0 | 0 | 0 | 0
|  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 1
[5 empty] | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
| 2020-08-03 | 3 | 0 | 2020-08-04 | 3 | 0 | 2020-08-05 | 3 | 0 | 2020-08-06 | 3 | 0 | 2020-08-07 | 3 | 0 | 2020-08-08 | 3 | 0 | 2020-08-09 | 0 | 0 | 0 | 0
|  | 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 2
|  | 1 |  |  | 2 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
[8 empty] | 1 |  |  | 1 |  |  | 1
| 2020-08-10 | 3 | 0 | 2020-08-11 | 3 | 0 | 2020-08-12 | 3 | 0 | 2020-08-13 | 3 | 0 | 2020-08-14 | 3 | 0 | 2020-08-15 | 2 | 0 | 2020-08-16 | 0 | 0 | 0 | 0
|  | 2 |  |  | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 2
|  | 1 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 1
1
| 2020-08-17 | 0 | 0 | 2020-08-18 | 0 | 0 | 2020-08-19 | 0 | 0 | 2020-08-20 | 0 | 0 | 2020-08-21 | 0 | 0 | 2020-08-22 | 0 | 0 | 2020-08-23 | 0 | 0 | 0 | 0
| 2020-08-24 | 0 | 0 | 2020-08-25 | 3 | 0 | 2020-08-26 | 3 | 0 | 2020-08-27 | 4 | 0 | 2020-08-28 | 3 | 0 | 2020-08-29 | 3 | 0 | 2020-08-30 | 0 | 0 | 16 | 0
|  |  |  | 77 line Head end | 1 | 0 | 77 line stringers | 1 |  | Transfer cv 1 & 2 rollers | 1 |  | 77 Line Piping | 2 |  | Transfer cv1 & 2 Grating | 1
|  |  |  | Transfer 1 Head chute | 1 | 0 | 77 line Head end chute | 1 |  | 77 line Piping Brackets | 2 |  | 77 line Take up Structure | 1 |  | 77 line Take up Structure | 2
|  |  |  | 77 Line Trestles | 1 | 0 | Transfer 1 Head chute | 1 |  | Decline Pipe brackets | 1
| 2020-08-31 | 3 | 0 | 2020-09-01 | 3 | 0 | 2020-09-02 | 3 | 0 | 2020-09-03 | 3 | 0 | 2020-09-04 | 3 | 0 | 2020-09-05 | 0 | 0 | 2020-09-06 | 0 | 0 | 15 | 0
| 77 line Take up Structure | 2 |  | 77 line stringers | 2 |  | Transfer 1 Head chute | 1 |  | 77 Idler Brackets | 2 |  | 77 Line Idler rollers | 2
| 77 Line Trestles | 1 |  | 77 Line Trestles | 1 |  | 77 line Head end | 1 |  | 77 line stringers | 1 |  | 77 Line Trestles | 1
[7 empty] | Decline Pipe brackets | 1
[9 empty] | Burger & Co. Site Manager: |  |  | P vd Merwe
Client Project Manager:

## Sep 20 (hidden)
1099: Burger & Olivier 74 Section Logistics - September 2020
| Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
Work Area | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
|  | 2 | 0 | 2020-09-01 | 3 | 0 | 2020-09-02 | 3 | 0 | 2020-09-03 | 3 | 0 | 2020-09-04 | 3 | 0 | 2020-09-05 | 2 | 0 | 2020-09-06 | 0 | 0 | 0 | 0
|  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 1
[5 empty] | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
Work Area | 2020-09-07 | 11 | 0 | 2020-09-08 | 9 | 0 | 2020-09-09 | 9 | 0 | 2020-09-10 | 9 | 0 | 2020-09-11 | 10 | 0 | 2020-09-12 | 2 | 0 | 2020-09-13 | 0 | 0 | 0 | 0
77 line 27 west | Top of TIP Bulk Bags | 3 |  | Top of TIP Bulk Bags | 3 |  | Top of TIP Bulk Bags | 3 |  | Top of TIP Bulk Bags | 3 |  | Top of TIP Bulk Bags | 3 |  | 77 line stringers, trestles | 2
| New Crusher Bulk Bags | 1 |  | New Crusher Bulk Bags | 1 |  | New Crusher Bulk Bags | 1 |  | New Crusher Bulk Bags | 1 |  | New Crusher Bulk Bags | 1
| Tip Top Winch | 1 |  | Tip Bottom Canopy Steel | 1 |  | Tip Bottom Canopy Steel | 1 |  | 77 Line Take Up Steel | 1 |  | MCC202 Bulk Bags | 1
| 77 line stringers, trestles | 1 |  | 77 Line Take Up Steel | 1 |  | 77 line stringers, trestles | 1 |  | CV53 Conveyor Belt | 1 |  | MCC202 Mesh | 1
| 77 Line Take Up Steel | 1 |  | Pipe brackets Flatbed only | 1 |  | CV53 Conveyor Belt | 1 |  | MCC202 Bulk Bags | 1 |  | Pipe brackets Flatbed only | 1
| 77 line Piping Brackets FW | 1 |  | 8 West Trf1 Winch | 1 |  | 77 Line Take Up Steel | 1 |  | 8 West Long Beam Flatbed UG | 1 |  | CV53 Conveyor Belt | 1
| 8 West Trf1 steel | 1 |  | 8 West Trf1 Grating, Handrail | 1 |  | 8 West Long Beam Flatbed UG | 1 |  | MCC202 Mesh | 1 |  | Minisub 20 | 1
| Pipes New Crusher | 1 | [10 empty] | 77 Line 200NB Pipes | 1
| CV53 Pulleys | 1
Work Area | 2020-09-14 | 0 | 0 | 2020-09-15 | 0 | 0 | 2020-09-16 | 0 | 0 | 2020-09-17 | 0 | 0 | 2020-09-18 | 0 | 0 | 2020-09-19 | 0 | 0 | 2020-09-20 | 0 | 0 | 0 | 0
| Tip Top Bulk Bags | 2 |  | Tip Top Bulk Bags | 2 |  | Tip Top Bulk Bags | 2 |  | Tip Top Bulk Bags | 2 |  | Tip Top Bulk Bags | 2 |  | Tip Top Bulk Bags | 2
| Tip Top Cement | 1 |  | Tip Top Cement | 1 |  | Tip Top Cement | 1 |  | Tip Top Cement | 1 |  | Tip Top Cement | 1 |  | Tip Top Cement | 1
| Tip Top Rebar | 1 |  | Tip Top Rebar | 1 |  | New Crusher Rebar | 1 |  | New Crusher Rebar | 1 |  | New Crusher Rebar | 1 |  | 77 Line 80NB Pipes | 1
| 77 Line 200NB Pipes | 1 |  | 77 Line 80NB Pipes | 1 |  | 77 Line 200NB Pipes | 1 |  | 77 Line 80NB Pipes | 1 |  | 77 Line 200NB Pipes | 1 |  | 77 Idler Brackets, Rollers | 1
| 8 West Trf1 Guards | 1 |  | 77 Idler Brackets, Rollers | 1 |  | 77 Idler Brackets, Rollers | 1 |  | 77 Idler Brackets, Rollers | 1 |  | 77 Idler Brackets, Rollers | 1
| 77 Idler Brackets, Rollers | 1 |  | 77 line stringers, trestles | 1
77 Take Up
Work Area | 2020-09-21 | 0 | 0 | 2020-09-22 | 0 | 0 | 2020-09-23 | 0 | 0 | 2020-09-24 | 0 | 0 | 2020-09-25 | 0 | 0 | 2020-09-26 | 0 | 0 | 2020-09-27 | 0 | 0 | 0 | 0
Bottom of Tip | 6 x 9 Planks | 1 | [7 empty] | R&R |  |  | R&R |  |  | R&R |  |  | R&R
Top of Tip
77 line 8 west | Idler frames | 2 |  | Rollers | 2
77 line 27 west
77 line 58 west
8 west |  |  |  | CV belt stand | 1
Crusher
Old crusher
Decline extetion
Work Area | 2020-09-28 | 3 | 0 | 2020-09-29 | 3 | 0 | 2020-09-30 | 3 | 0 |  | 3 | 0 |  | 3 | 0 |  | 3 | 0 |  | 0 | 0 | 18 | 0
Bottom of Tip
Top of Tip
77 line 8 west | [12 empty] | Trestles and stringers | 1 |  | 200 NB piping | 1
77 line 27 west | Idler frames | 2 |  | Rollers | 3 | [7 empty] | Trestles and stringers | 1 |  | 200 NB piping | 1
77 line 58 west | [6 empty] | Idler frames | 3 |  | Rollers | 3 |  | Trestles and stringers | 1 |  | 201 NB piping | 1
8 west | CV belt | 1
Crusher
Old crusher
Decline extetion
Work Area |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | Burger & Co. Site Manager: |  |  | P vd Merwe
Client Project Manager:

## Oct 20 (hidden)
Burger & Co 74 section Logistics
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
Work Area | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
|  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2020-10-01 | 0 | 0 | 2020-10-02 | 0 | 0 | 2020-10-03 | 0 | 0 | 2020-10-04 | 0 | 0 | 0 | 0
Work Area | 2020-10-05 | 0 | 0 | 2020-10-06 | 0 | 0 | 2020-10-07 | 0 | 0 | 2020-10-08 | 0 | 0 | 2020-10-09 | 0 | 0 | 2020-10-10 | 0 | 0 | 2020-10-11 | 0 | 0 | 0 | 0
Work Area | 2020-10-12 | 0 | 0 | 2020-10-13 | 0 | 0 | 2020-10-14 | 0 | 0 | 2020-10-15 | 0 | 0 | 2020-10-16 | 0 | 0 | 2020-10-17 | 0 | 0 | 2020-10-18 | 0 | 0 | 0 | 0
Work Area | 2020-10-19 | 0 | 0 | 2020-10-20 | 0 | 0 | 2020-10-21 | 0 | 0 | 2020-10-22 | 0 | 0 | 2020-10-23 | 0 | 0 | 2020-10-24 | 0 | 0 | 2020-10-25 | 0 | 0 | 0 | 0
Work Area | 26 10 2020 - Big Pour Day | 0 | 0 | 2020-10-27 | 0 | 0 | 2020-10-28 | 0 | 0 | 2020-10-29 | 0 | 0 | 2020-10-30 | 0 | 0 | 2020-10-31 | 0 | 0 |  | 0 | 0 | 0 | 0
Work Area |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | Burger & Co. Site Manager: |  |  | P vd Merwe
Client Project Manager:

## Nov 20 (hidden)
Burger & Co 74 section Logistics
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
Work Area | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
|  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2020-11-01 | 0 | 0 | 0 | 0
Work Area | 2020-11-02 | 0 | 0 | 2020-11-03 | 0 | 0 | 2020-11-04 | 0 | 0 | 2020-11-05 | 0 | 0 | 2020-11-06 | 0 | 0 | 2020-11-07 | 0 | 0 | 2020-11-08 | 0 | 0 | 0 | 0
Work Area | 2020-11-09 | 0 | 0 | 2020-11-10 | 0 | 0 | 2020-11-11 | 0 | 0 | 2020-11-12 | 0 | 0 | 2020-11-13 | 0 | 0 | 2020-11-14 | 0 | 0 | 2020-11-15 | 0 | 0 | 0 | 0
Work Area | 2020-11-16 | 0 | 0 | 2020-11-17 | 0 | 0 | 2020-11-18 | 0 | 0 | 2020-11-19 | 0 | 0 | 2020-11-20 | 0 | 0 | 2020-11-21 | 0 | 0 | 2020-11-22 | 0 | 0 | 0 | 0
Work Area | 2020-11-23 | 0 | 0 | 2020-11-24 | 0 | 0 | 2020-11-25 | 0 | 0 | 2020-11-26 | 0 | 0 | 2020-11-27 | 0 | 0 | 2020-11-28 | 0 | 0 | 2020-11-29 | 0 | 0 | 0 | 0
Work Area | 2020-11-30 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | Burger & Co. Site Manager: |  |  | P vd Merwe
Client Project Manager:
Formulas:
Tuesday = [Monday]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1
Saturday = [Friday]+1
Sunday = [Saturday]+1

## Dec 20 (hidden)
Burger & Co 74 section Logistics
|  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  |  | Loads |  | Weekly Loads
|  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual |  | Planned | Actual | Planned | Actual
Work Area | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday |  |  | Saturday |  |  | Sunday |  |  | Total
|  | 0 | 0 | 2020-12-01 | 0 | 0 | 2020-12-02 | 0 | 0 | 2020-12-03 | 0 | 0 | 2020-12-04 | 0 | 0 | 2020-12-05 | 0 | 0 | 2020-12-06 | 0 | 0 | 0 | 0
Work Area | 2020-12-07 | 0 | 0 | 2020-12-08 | 0 | 0 | 2020-12-09 | 0 | 0 | 2020-12-10 | 0 | 0 | 2020-12-11 | 0 | 0 | 2020-12-12 | 0 | 0 | 2020-12-13 | 0 | 0 | 0 | 0
Year End Closure
Work Area | 2020-12-14 | 0 | 0 | 2020-12-15 | 0 | 0 | 2020-12-16 | 0 | 0 | 2020-12-17 | 0 | 0 | 2020-12-18 | 0 | 0 | 2020-12-19 | 0 | 0 | 2020-12-20 | 0 | 0 | 0 | 0
Work Area | 2020-12-21 | 0 | 0 | 2020-12-22 | 0 | 0 | 2020-12-23 | 0 | 0 | 2020-12-24 | 0 | 0 | 2020-12-25 | 0 | 0 | 2020-12-26 | 0 | 0 | 2020-12-27 | 0 | 0 | 0 | 0
Work Area | 2020-12-28 | 0 | 0 | 2020-12-29 | 0 | 0 | 2020-12-30 | 0 | 0 | 2020-12-31 | 0 | 0 | 2021-01-01 | 0 | 0 | 2021-01-02 | 0 | 0 | 2021-01-03 | 0 | 0 | 0 | 0
Work Area | 2021-01-04 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
[9 empty] | Burger & Co. Site Manager: |  |  | P vd Merwe
Client Project Manager:
Formulas:
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1
Saturday = [Friday]+1
Sunday = [Saturday]+1
Tuesday = [Monday]+1

## SUMMARY
NC3C044-N3 Charging Bays II
|  |  |  | Total | 2025-08-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01
|  | Unit of Measure | Total QTY | Planned Loads Based on UV Load | Loads | Loads | Loads | Loads | Loads | Loads | Loads | Loads | Loads | Loads
| Material |  |  |  | 25 | 65 | 91 | 87 | 87 | 41 | 52 | 57 | 49 | 44
Concrete Works | Bulk Bags | No | 2490 | 415 | 20 | 35 | 50 | 65 | 65 | 30 | 30 | 40 | 40 | 40
| Cement | Pallets | 187 | 94 | 5 | 14 | 15 | 15 | 17 | 8 | 8 | 4 | 4 | 4
| Reinforcing | Ton | 4 | 2 |  | 1 | 1
| Mesh | Sheets | 215 | 11 |  | 4 | 4 | 3
Brick Work | Bricks | Pallets | 33 | 17 |  | 7 | 10
| Sand | No | 40 | 7 |  |  | 7
| Building material ( Doors, Window Etc.) | No |  | 8 |  | 4 | 4
Structural Steel | Structural Steel | Ton | 43 | 21 |  |  |  | 4 | 5 | 3 | 3 | 3 | 3
Piping | Pipes | M | 116 | 7 | [6 empty] | 4 | 3
Electrical Equipment | Electrical Equipment | No |  | 6 | [6 empty] | 3 | 3
Mechanical Equipment | Mechanical Equipment | No |  | 10 | [6 empty] | 4 | 4 | 2
Note on F3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on G3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on H3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on I3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on J3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on K3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on L3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on M3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on N3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on O3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on P3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site

## Jan 2024 (hidden)
Heading
[12 empty] | Total |  |  |  | 2024-01-15 |  |  |  | 2024-01-16 |  |  |  | 2024-01-17 |  |  |  | 2024-01-18 |  |  |  | 2024-01-19 |  |  |  | 2024-01-20 |  |  |  | 2024-01-21 |  |  |  | 2024-01-22 |  |  |  | 2024-01-23 |  |  |  | 2024-01-24 |  |  |  | 2024-01-25 |  |  |  | 2024-01-26 |  |  |  | 2024-01-27 |  |  |  | 2024-01-28 |  |  |  | 2024-01-29 |  |  |  | 2024-01-30 |  |  |  | 2024-01-31
[12 empty] | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity |  |  | Loads | Quantity
Sub section | Laydown Area | Area | Discipline | Section | Activity ID | Baseline Start | Baseline Finish | Start | Finish | Material | Unit of Measure | 7 | Planned | Actual | Variance | 3 | Planned | Actual | Variance | 4 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance | 0 | Planned | Actual | Variance
Soffit Concrete Support | General | Tip & Crusher Chamber | Civil | Tip | WMNB1950 | 2024-01-16 | 2024-01-19 | 2024-01-18 | 2024-01-24 | Rebar | Tons | 0 | 15 | 5 | -10 | 0 | 10 | 5 | -5 |  | 5 |  | -5 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Soffit Concrete Support | Lift 1 | Tip & Crusher Chamber | Civil | Tip | WMNB1950 | 2024-01-16 | 2024-01-19 | 2024-01-18 | 2024-01-24 | Shutters | Number | 3 | 10 | 10 | 0 | 3 | 10 | 10 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Soffit Concrete Support | Lift 1 | Tip & Crusher Chamber | Civil | Tip | [5 empty] | Bulkbags | Number | 3 | 200 | 0 | -200 |  |  |  | 0 | 3 | 200 |  | -200 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Soffit Concrete Support | General | Tip & Chrusher Chamber | Civil | Tip | [5 empty] | Cement | Number | 1 | 10 | 0 | -10 |  |  |  | 0 | 1 | 10 |  | -10 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Soffit Concrete Support | Lift 2 | Tip & Chrusher Chamber | Civil | Tip | [5 empty] | Bulkbags | Number | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Grizzle |  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber | Civil | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber |  | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Tip & Chrusher Chamber |  | Tip | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Note on N3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site
Note on R3: Do want to manage the number of loads required for the quantity or which of the 4 loads we want to uitlise to get the materials to site