| PART A – REFERENCE INFORMATION |  |  |  |
| --- | --- | --- | --- |
| Operation Name | Assmang Black Rock Mine Operations | Vote No. | TBC |
| Application Date | 08 December 2025 | Project Leader | Greg Karsten |
| Project Title | Conveyor Belt Bearing Temperature Monitoring System |  |  |
| Project Value | R 11,460,000.00 |  |  |
| Project Start Date | January 2026 | Project End Date | June 2026 |

Capital Approval Level

☐ Senior General Manager and Financial Manager

☒ Executive Operations (Mines) and Senior Executive Finance

☐ One ARM and One Assore Exco Member

☐ Two ARM and Two Assore Exco Members

☐ Board Approval

Type of Capital

☐Consolidated Assessment		☒Capital Application	☐Replacement Capital

EXECUTIVE SUMMARY

The Department of Mineral and Petroleum Resources (DMPR) has issued a directive from the DMPR principal inspector for real-time bearing temperature monitoring on all conveyor belt infrastructure. This capital application seeks approval for the installation of Dynamox wireless bearing temperature monitoring systems across Nchwaning 2, Nchwaning 3, and Gloria operations. Current Compliance Status: Non-compliant. BRMO operations lack continuous bearing temperature monitoring on conveyor systems, creating regulatory risk and potential enforcement action by DMPR inspectorate. Technology Solution: Dynamox triaxial vibration and temperature monitoring sensors with wireless gateway infrastructure, providing real-time condition monitoring, automated failure detection, and remote prognosis capabilities integrated with existing maintenance management systems. Scope Coverage: • Nchwaning 2: 18 conveyor systems (226 plumber blocks total) • Nchwaning 3: Underground belt infrastructure (all split bearings on new drive pulleys) • Gloria: 4 primary conveyor systems (CV78, CV75, CV51, CV10) Regulatory Imperative: DMPR inspector directive - failure to implement monitoring creates Section 54 closure risk. Total Project Value: R11,460,000.00 Implementation Timeline: 6 months from approval (January-June 2026) Vendor: Supreme Marketing (Dynamox authorized distributor)

The DMPR principal inspector has directed that all conveyor belt systems at Assmang Black Rock Mine Operations implement real-time bearing temperature monitoring to enhance safety and prevent catastrophic failures. Current manual inspection practices do not satisfy the inspector's directive for continuous automated monitoring with immediate alarm capabilities.

This capital application addresses the directive through deployment of Dynamox wireless bearing temperature monitoring sensors across three operations:
• Nchwaning 2: 18 conveyor systems (226 bearing positions) - R5.3M
• Nchwaning 3: Decline belt fitted, remaining belts estimated R3.3M
• Gloria: 4 critical conveyor systems - R950k

The solution provides real-time temperature and vibration monitoring via cloud-based Live Online platform with automated diagnostics, mobile app access, and predictive maintenance capabilities.

Total Capital: R11,460,000
• Project Capital: R9,550,000
• Escalation (5%): R477,500
• Contingency (10%): R955,000
• Fees (5%): R477,500

Implementation: 6-month phased rollout (January-June 2026). Non-compliance with the inspector directive exposes BRMO to Section 54 safety stoppages. Single bearing failure on critical conveyors results in 8-24 hour stoppages with production losses exceeding 70,000 tonnes per month.

BUDGET SUMMARY

| Description | R | Percentage |
| --- | --- | --- |
| Project Capital (High level breakdown required of categories) | R 9,550,000.00 |  |
| Escalation | R 477,500.00 | 5% |
| Contingency | R 955,000.00 | 10% |
| Fees | R 477,500.00 | 5% |
| Total | R 11,460,000.00 |  |
| Amount in 5 Year Plan | R 0 (Out of Plan - DMPR Inspector Directive) |  |

CATEGORISATION:

| Complexity | ✓ | Guide | Project Value R’mil | ✓ |
| --- | --- | --- | --- | --- |
| High Complexity |  | Requires design, multi-disciplinary inputs and site construction work | >R500m |  |
|  |  |  | >R250m |  |
|  |  |  | >R70m |  |
|  |  |  | >R30m |  |
| Low Complexity | ✓ | Equipment related or provision of services where no design work is required | <R30m | ✓ |
|  |  |  | <R5m |  |

PART B – QUALITY ASSURANCE

Heads of Departments (HODs) or Specialists

| Name and Designation | Comment (from specialist and other stakeholders) | Signature |
| --- | --- | --- |
| Greg Karsten - Senior Production Engineer |  |  |
| Jacques Breet - Engineering Manager |  |  |
| N Ramlugan - Financial Manager |  |  |

| Designation | Recommended by | Signature | Recommendation signatures required |
| --- | --- | --- | --- |
| ARM Technical |  |  | Projects >R1m or as requested |
| Executive Operations Support |  |  | Projects >R5m |
| Executive Projects |  |  | Projects >R70m |

Recommendation Comments

PART C – APPROVALS

Signatories – Application is signed according to the Delegation of Authority

|  | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Operational Capital ≤R10m Out Of Plan |  |  |  |
| SGM |  |  |  |
| Financial Manager |  |  |  |
| Operational Capital >R10m ≤R15m Out Of Plan |  |  |  |
| Executive Operations (Mines): | TBC |  |  |
| Senior Executive Finance | TBC |  |  |
| EXCO >R15m ≤R30m Out Of Plan |  |  |  |
| ARM EXCO member 1 |  |  |  |
| Assore EXCO member 1 |  |  |  |
| EXCO >R30m ≤R60m Out Of Plan |  |  |  |
| ARM EXCO member 2 |  |  |  |
| Assore EXCO member 2 |  |  |  |
| Board Approval >R60m Out of Plan |  |  |  |
| Company Secretary |  |  |  |

Approvals Signatories Commentary

PART D – MOTIVATION

- Project Background

The DMPR (Department of Mineral and Petroleum Resources) has directed real-time bearing temperature monitoring on all conveyor belt systems as part of enhanced mine safety and equipment reliability regulations. This directive arose from industry-wide incidents of bearing failures leading to belt fires, production stoppages, and safety incidents.

Current State: BRMO operations rely on manual temperature inspections during routine maintenance intervals, creating gaps in continuous monitoring and delayed failure detection. This reactive approach does not satisfy the DMPR principal inspector's directive for real-time monitoring.

Regulatory Context: DMPR inspections have identified the absence of continuous bearing temperature monitoring as a compliance gap. Failure to address this mandate exposes BRMO to:
• Section 54 safety stoppages

This capital investment transitions BRMO from reactive manual inspections to proactive predictive maintenance aligned with DMPR requirements and modern asset reliability standards.

- SCOPE OF THE PROJECT

Installation of Dynamox wireless bearing temperature and vibration monitoring systems across three operational sites:

System Components Per Installation:
• TcAs Sensors: Simultaneous temperature and triaxial vibration monitoring (up to 2.5 kHz)
• HF+2 Sensors: High-frequency vibration and temperature monitoring (up to 13 kHz)
• DynaGateway DUO: Bluetooth wireless data collectors (100m range, unlimited sensors per gateway)
• Mounting hardware: Stainless steel bases, spacers, adhesive mounting systems
• Installation services: OEM-certified installation teams, baseline commissioning
• Software platform: Live Online cloud-based monitoring, automated diagnostics, mobile access

Site-Specific Scope:

Nchwaning 2:
• 18 conveyor systems monitored
• 226 plumber blocks instrumented
• Conveyor systems: Crusher feed belt, Orepass feed belt, NR1-NR11 conveyors, ST07, US01-02, LS01-02
• Multiple gateway deployment for full site coverage

Nchwaning 3:
• Underground decline belt infrastructure
• All split bearings on new belt drive pulleys
• Expansion-ready for future underground development

Gloria:
• 4 primary conveyor systems: CV78, CV75, CV51, CV10
• 52 plumber blocks total
• Surface conveyor infrastructure

Deliverables:
• Fully commissioned monitoring systems with 24/7 operational capability
• Integration with Live Online predictive maintenance platform
• Baseline vibration and temperature signatures for all monitored bearings
• Operator training on system interpretation and alarm response
• 12-month warranty on all hardware and installation workmanship

- ALTERNATIVES CONSIDERED

Alternative 1: Continue Manual Inspections - Rejected
• Does not satisfy DMPR principal inspector directive for real-time monitoring
• Reactive failure detection creates unplanned downtime risk
• Insufficient for modern asset reliability requirements
• Exposes BRMO to regulatory enforcement action

Alternative 2: Wired Temperature Monitoring Systems - Rejected
• Higher installation cost due to cabling infrastructure requirements
• Limited scalability for future expansion
• Maintenance complexity and cable failure modes
• Longer installation timeline requiring extended production interruptions

Alternative 3: Alternative Sensor Vendors (SKF, Schaeffler, etc.) - Rejected
• Higher per-sensor cost (R15k-R25k vs R7.5k-R11k for Dynamox)
• Limited wireless range requiring more gateway infrastructure

Alternative 4: Phased Implementation (Year 1: Critical belts only) - Rejected
• Does not achieve compliance with DMPR inspector directive across all conveyor systems
• Deferred regulatory risk
• Marginal cost savings insufficient to justify extended non-compliance period

Selected Option: Full Dynamox Deployment
• compliant with DMPR inspector directive real-time monitoring across all sites
• Proven N3 decline belt proof-of-concept performance
• Wireless technology minimizes installation complexity
• Scalable architecture supports future expansion
• Integration with existing Live Online maintenance platform
• Competitive pricing with established local support (Supreme Marketing)
• ISO 9001, 27001, 27701, 27018 certified solution

- Business case

This is a inspector directive-driven capital requirement directed by the DMPR principal inspector. The business case is grounded in risk avoidance, regulatory compliance, and operational reliability enhancement rather than traditional ROI metrics.

Primary Drivers:

1. DMPR Inspector Directive Compliance:
  • DMPR principal inspector directive for real-time monitoring compliance
  • Elimination of Section 54 closure risk

2. Production Risk Mitigation:
  • Bearing failures cause unplanned belt stoppages averaging 8-24 hours per incident
  • Early failure detection enables planned maintenance interventions during scheduled downtime
  • Transition from reactive to predictive maintenance philosophy

3. Safety Enhancement:
  • Bearing failures create fire risk (overheating, friction ignition)
  • Real-time alarm systems enable immediate intervention
  • Reduced personnel exposure to manual temperature inspection hazards

4. Asset Life Extension:
  • Early detection prevents catastrophic bearing failures
  • Optimized lubrication intervals based on actual bearing condition
  • Reduced secondary damage to pulleys, belts, and gearboxes from failed bearings

- BUSINESS DELIVERABLES

• compliant with DMPR inspector directive real-time bearing temperature monitoring on all conveyor systems
• 24/7 automated condition monitoring with threshold-based alarm generation
• Cloud-based Live Online platform access (desktop and mobile applications)
• Baseline vibration and temperature signatures for all 280+ monitored bearings
• Automated failure prediction and diagnostic reports (DynaDetect algorithm)
• Operator training on system interpretation and maintenance response protocols
• Transition from reactive to predictive bearing maintenance philosophy
• Scalable infrastructure supporting future conveyor system additions
• Historical trending data enabling root cause analysis of bearing failures
• Remote prognosis capability for specialist vibration analysis support

Key Performance Indicators:
• 100% compliance with DMPR inspector directive
• Reduction in unplanned belt stoppages due to bearing failures (target: 50% reduction Year 1)
• Early bearing failure detection rate (target: 90%+ pre-failure warnings)
• Alarm response time <30 minutes from temperature threshold exceedance
• System uptime >98% (sensor and gateway availability)

- FINANCIAL MOTIVATION

This project is driven by regulatory compliance mandates rather than traditional financial return metrics. The value proposition is risk avoidance, regulatory compliance maintenance, and operational continuity protection.

Assumptions:

• Vendor pricing valid for 90 days from quotation date (17 Nov 2025)
• Installation can be executed during planned maintenance windows without production impact
• Existing 220V electrical infrastructure available at gateway locations
• Network coverage adequate for cloud data transmission

| Net Present Value (NPV) | N/A - Regulatory compliance project |
| --- | --- |
| Internal Rate of Return (IRR) | N/A - Regulatory compliance project |
| Pay Back Period | N/A - Regulatory compliance project |

CASHFLOW ESTIMATE

Phased Expenditure (January-June 2026):

**Phase 1: Nchwaning 2 (Jan-Mar 2026):** R 5,300,000.00
• Hardware procurement: 60 days lead time
• Installation: 19 days on-site (20-25 sensors/day, 2-person teams)
• Commissioning and baseline: 2 weeks

**Phase 2: Gloria (Mar-Apr 2026):** R 950,000.00
• Hardware procurement: concurrent with N2 order
• Installation: 7 days on-site
• Commissioning and baseline: 1 week

**Phase 3: Nchwaning 3 (Apr-Jun 2026):** R 3,300,000.00
• Underground infrastructure coordination
• Installation: 7 days on-site
• Integration with existing N3 decline proof-of-concept systems

**Payment Terms (per Supreme Marketing quotation):**
• Hardware: Standard 30-day payment terms
• Installation services: Progressive payments upon completion milestones
• Travel/accommodation: Reimbursable upon invoice submission

**Capital Commitment Timeline:**
• January 2026: 40% (hardware orders)
• March 2026: 35% (N2 and Gloria installation completion)
• June 2026: 25% (N3 installation completion, project close-out)

Total Project Budget: R 11,460,000.00
Funding Source: FY2025/26 Unplanned Operational Capital

- Technical Summary

The Dynamox ecosystem provides comprehensive predictive maintenance capabilities through wireless sensor technology, cloud-based analytics, and automated diagnostics. System architecture proven through N3 decline belt proof-of-concept installation (performing exceptionally per site feedback).

## Geology and Mineral Resources

N/A - Asset reliability and monitoring infrastructure

## Mining Method and plan summary

N/A - Conveyor monitoring systems do not impact mining method. Systems support ore handling infrastructure reliability.

## Metallurgical

N/A

## Site and infrastructure

N/A - Gateways mount to existing conveyor structures. No new infrastructure required.

## Civil & Earthworks

N/A - No civil works required. Gateway enclosures mount to existing structures.

## Structural

N/A - Wireless gateways mount to existing conveyor structural steel or building walls. Sensor bonding does not impact structural integrity of bearing housings.

## Mechanical

Mounting Hardware:
• Stainless steel bases custom-fitted to bearing housing geometry
• High-temperature epoxy adhesive (thermally stable to 150°C)
• 24-hour cure time before system commissioning

## Control and Instrumentation

Software Platform: Live Online (Dynamox Cloud Platform)
• Real-time data visualization (web and mobile applications)
• Automated failure detection algorithms (DynaDetect)
• Configurable alarm thresholds (temperature and vibration)
• Email/SMS alert notification system
• Historical trend analysis and reporting
• API integration capability for CMMS systems

Data Architecture:
• Sensor → Gateway (Bluetooth wireless, 100m range)
• Gateway → Cloud 
• Cloud → User devices (HTTPS secure connections)
• Data retention: Unlimited historical storage

Monitoring Capabilities:
• DynaSens: Mobile inspection route management
• DynaDash: Specialized asset health dashboards
• DynaDetect: Automated diagnosis and failure prediction
• DynaNeo: Visual plant management and asset flow monitoring

System Integration:
• CSV and JSON data export for external systems
• API access (standard or customized integration)
• Ready-to-use metrics and KPIs
• Integration with existing Live Online platform (N3 decline belt system)

Alarm Management:
• Multi-level threshold configuration (warning, critical)
• Escalation protocols for alarm response
• Alarm acknowledgment and resolution tracking
• False alarm filtering algorithms

## Electrical

Power Requirements:
• Gateway: 220V AC, <50W average consumption
• Sensors: Battery-powered (5-year typical battery life, user-replaceable)
• No additional electrical infrastructure required

Communication:
• Gateway cellular modem: 4G LTE (Vodacom/MTN network compatible)
• Antenna: External stub antenna (gateway enclosure mounted)
• Data consumption: <500MB per gateway per month

Installation Electrical Work:
• Gateway power connections: Standard 220V single-phase outlets
• Circuit protection: 10A MCB per gateway
• Earth/ground connections as per mine electrical standards
• Lightning protection: Per existing conveyor structure earthing systems

## Fire Control

NA

- OTHER PROJECT CONSIDERATIONS

## Marketing

N/A

## Legal & Fiscal

Regulatory Compliance:
• DMPR principal inspector directive for real-time bearing monitoring
• Mine Health and Safety Act (MHSA) compliance

Procurement:
• Supreme Marketing: Dynamox authorized distributor for South Africa
• Quotations QU101520 (hardware/installation) and QU101521 (remote prognosis service)
• Standard BRMO procurement policies and Delegation of Authority
• Vendor registration number: 40021298
• Vendor VAT number: 4810214793

Intellectual Property:
• Dynamox software platform: Licensed SaaS model (no license fees, no annual subscription)
• Data ownership: BRMO retains full ownership of all collected monitoring data
• Export capability: CSV and JSON formats for external analysis

Warranty:
• Hardware: 12 months manufacturer warranty from commissioning date
• Installation workmanship: 12 months warranty
• Software platform: Continuous updates and improvements (no version obsolescence)

## Human Resources

No additional permanent personnel required. Monitoring system managed within existing maintenance and engineering teams.

Training Requirements:
• System administrators (2x Engineering staff): 2-day intensive training on Live Online platform, alarm management, report generation
• Maintenance supervisors (6x personnel): 1-day orientation on system capabilities, alarm interpretation, maintenance response protocols
• Operators (8x WEDs and conveyor operators): 4-hour briefing on mobile app usage, alarm acknowledgment procedures

Training Delivery:
• On-site training during system commissioning phase
• Supreme Marketing/Dynamox training team
• Training materials provided (user manuals, quick reference guides)
• Ongoing technical support via Supreme Marketing

Operational Impact:
• Reduced manual temperature inspection requirements (vibration analysis rounds still required)
• Faster failure detection and diagnosis (alarm-driven response)
• Enhanced predictive maintenance planning capabilities

## Safety and Health

Project Safety:
• All installation contractors comply with BRMO Mine Safety Rules
• Risk assessments required before work commencement
• Permit to Work system for conveyor access during installation
• Lock-out procedures for powered conveyors
• Scaffolding and working at height protocols (where applicable)
• Passport 360 safety orientation for all contractor personnel

Environmental

Environmental Impact Assessment:
• Minimal environmental footprint (wireless technology, low power consumption)
• No chemical processes or emissions
• No excavation or civil works required

## Sustainable development

- NA

## Procurement

Procurement: Direct award to Supreme Marketing (Dynamox authorized distributor)

Justification:
• Proven technology through N3 decline belt proof-of-concept installation
• Dynamox single-source OEM for proprietary sensor technology
• Supreme Marketing established relationship with BRMO (vendor 40021298)
• Competitive pricing validated against international benchmarks
• Local technical support capability (Rustenburg-based)

Procurement Documentation:
• Quotation QU101520: Hardware and installation services (R102,948 budget quote per sensor package)
• Quotation QU101521: Remote prognosis service (R7,629.10 annual per sensor)
• Vendor registration: Complete and current
• Detailed capital estimate: Excel breakdown by site and conveyor system

Payment Terms:
• Hardware: 30-day standard payment terms
• Installation: Progressive payments upon milestone completion
• Travel and accommodation: Reimbursable upon invoice submission

Vendor Management:
• Contract administration: BRMO Supply Chain
• Technical liaison: Engineering Department (Greg Karsten project leader)
• Payment processing: Finance Department (N Ramlugan approval authority).

## Ongoing operational cost

Live Online platform provides automated diagnostics included with hardware purchase at no additional cost. Remote prognosis adds human specialist review for complex failure modes.

Maintenance Costs:
• Sensor battery replacement: 5-year cycle, ~R200 per sensor (self-service)
• Adhesive replacement: Minimal (sensor relocation rare)
• No software license fees or subscription costs

- Project Management summary

Project Execution Strategy: Phased deployment across three sites with sequential installation to minimize resource concentration and enable lessons-learned implementation.

Project Leadership:
• Project Leader: Greg Karsten (Engineering Department)
• Technical Oversight: Jacques Breet (Engineering Manager)

Execution Phases:

Phase 1 - Nchwaning 2 (Jan-Mar 2026):
• Hardware procurement: 60-day lead time from PO
• Site preparation: Gateway mounting locations, electrical connections
• Installation: 19-day on-site program (20-25 sensors/day installation rate)
• Commissioning: 2-week baseline measurement and threshold configuration
• Training: 2-day system administrator intensive, 1-day supervisor orientation

Phase 2 - Gloria (Mar-Apr 2026):
• Concurrent hardware procurement with N2 order
• Installation: 7-day on-site program (4 conveyor systems)
• Commissioning: 1-week baseline and integration
• Training: Operator briefings and mobile app orientation

Phase 3 - Nchwaning 3 (Apr-Jun 2026):
• Underground access coordination with production schedule
• Installation: 7-day on-site program
• Integration with existing N3 decline proof-of-concept system
• Final system validation and project closeout

Risk Management:
• Hardware lead time risk: Early procurement initiation upon capital approval
• Access restrictions: Installation scheduling during planned maintenance windows
• Weather (surface installations): Adhesive curing temperature requirements (>10°C ambient)
• Resource availability: Supreme Marketing installation team committed dates
• Testing and commissioning: Contingency time for system optimization

## Schedule

Project Timeline: January 2026 - June 2026 (6 months)

Float/Contingency: 2 weeks built into commissioning phases for system optimization and issue resolution.

## Project RESOURCES

Internal BRMO Resources:

Project Management:
• Greg Karsten - Project Leader (Engineering Department)
• Time allocation: 25% FTE during implementation phase
• Responsibilities: Vendor coordination, technical oversight, stakeholder communication

Engineering Support:
• Jacques Breet - Engineering Manager (Technical approval and oversight)
• Greg Karsten - Senior Production Engineer (Operational coordination)
• Time allocation: 10% FTE during installation phases

Maintenance Coordination:
• Site maintenance supervisors (N2, N3, Gloria) - Access coordination, production scheduling
• Electricians (gateway installations) - 5 days per site
• Riggers/fitters (platform access for sensor mounting) - As required

Operational Readiness requirements

BRMO Operational Readiness Assessment: HIGH

Infrastructure Readiness:
• Electrical: 220V outlets available at all proposed gateway locations
• Communications: Wifi network coverage validated across all sites

• Access: Conveyor walkways and platforms suitable for sensor installation
• Safety: Existing procedures accommodate new monitoring requirements

Maintenance Integration:
• Live Online platform accessible to existing maintenance personnel
• Alarm escalation protocols defined and documented
• Maintenance response procedures updated to include bearing temperature alerts
• CMMS integration roadmap defined (future enhancement)

Training Completion Criteria:
• 2x System administrators certified on Live Online platform administration
• 6x Maintenance supervisors trained on alarm interpretation and response
• 8x Operators oriented on mobile app usage and alarm acknowledgment
• Training documentation and user manuals distributed

Operational Handover Requirements:
• As-built documentation (sensor locations, gateway IP addresses, system architecture)
• Baseline vibration and temperature reports for all monitored bearings
• Alarm threshold configuration documentation
• Vendor contact list and escalation procedures (Supreme Marketing technical support)
• 12-month warranty certificate and warranty claim procedures

Risks

Project Risks and Mitigation Strategies:

Technical Risks:

1. Hardware Lead Time Delays (Medium probability, High impact)
  • Mitigation: Early PO placement upon capital approval, confirmed 60-day delivery from Supreme Marketing
  • Contingency: Phased delivery allows N2 installation to proceed while Gloria/N3 hardware in transit

2. Sensor Installation Quality (Low probability, Medium impact)
  • Mitigation: OEM-certified installation teams (Supreme Marketing), proven N3 proof-of-concept success
  • Contingency: 12-month warranty covers reinstallation of failed bonds

3. Gateway Communication Issues (Low probability, Medium impact)
  • Mitigation: Pre-installation site survey validates mobile coverage, backup gateway locations identified
  • Contingency: External antennas or alternate gateway positioning

Operational Risks:

4. Production Access Restrictions (Medium probability, Low impact)
  • Mitigation: Installation scheduling during planned maintenance windows, phased approach per belt
  • Contingency: Extended project timeline if production priorities require deferral

5. False Alarm Rate (Medium probability, Medium impact)
  • Mitigation: Conservative initial threshold settings, 30-day optimization period post-commissioning
  • Contingency: Threshold tuning and alarm filtering algorithm adjustment

- Conclusion and recommendation

The installation of Dynamox bearing temperature monitoring systems across Nchwaning 2, Nchwaning 3, and Gloria operations is a principal inspector directive compliance requirement imposed by the DMPR. This capital investment transitions BRMO from non-compliant manual inspection practices to real-time automated monitoring aligned with modern mining safety and asset reliability standards.

Key Justifications:

1. Regulatory requirement: DMPR inspector directive requires real-time bearing temperature monitoring. Non-compliance exposes BRMO to Section 54 stoppages, production curtailment, and .

2. Proven Technology: N3 decline belt proof-of-concept installation demonstrates exceptional system performance. Dynamox wireless architecture validated in BRMO operating environment.

3. Risk Mitigation: Investment of R11,460,000.00 prevents potential production losses exceeding R2.8M per day from regulatory stoppages. Single avoided major bearing failure incident provides breakeven justification.

4. Operational Enhancement: Transition from reactive manual inspections to predictive maintenance philosophy. Early failure detection enables planned interventions during scheduled maintenance windows.

5. Scalable Platform: Wireless infrastructure supports future expansion. Integration with existing Live Online asset management ecosystem proven.


Recommendation:

APPROVE this out-of-plan capital application for R11,460,000.00 to achieve full compliance with DMPR inspector directive across all conveyor belt infrastructure by June 2026.

Approval Level Required: One ARM and One Assore Exco Member (>R10m ≤R15m threshold per Delegation of Authority)

Urgency: Capital approval required January 2026 to enable hardware procurement (60-day lead time) and meet Q2 2026 compliance target. Delays in approval extend BRMO regulatory non-compliance period and associated exposure to DMPR enforcement action.

# Appendix 1 supporting documents as applicable

# Appendix 2 Specifications, Quotations, Bills of Quantities

2) Quotations and Budget Quotations