## Eng Weekly report
Weekly Summary Report
Shaft | Nchwaning 2 | [6 empty] | Plan YTD | Actual YTD | Plan MTD | Actual MTD | Variance
[7 empty] | ROM | 621085 | 534969 | 60105 | 38824 | -21281
Week - Date to | 2025-11-07 | 2025-11-13 |  |  |  |  | Product | 569862 | 527172 | 53761 | 38548 | -15213
Safety
| YTD | No wk | Remarks
MTC | 1 | 1 | Employee slipped and fell while descending steps from Mechanics tea room
LTI | 0 | 0
PD | 4 | 1 | LDO594 bumped against scaler while travelling to pumps at 17S dams
Incidents Reported | 0 | 0
Labour
| Plan | Actual | Leave | Not Specified | % AT Work |  | Remarks
Fri | 216 | 160 | 52 | 4 | 74.07%
Mon | 216 | 185 | 20 | 11 | 85.65%
Tue | 216 | 186 | 19 | 11 | 86.11%
Wed | 216 | 186 | 17 | 13 | 86.11%
Thur | 216 | 182 | 17 | 17 | 84.26%
Sat |  |  |  | 0 | #DIV/0!
Sun |  |  |  | 0 | #DIV/0!
Cost
COST By ELEMENT | MONTH ACTUAL | MONTH BUDGET | MONTH VAR | YTD ACTUAL | YTD BUDGET | YTD VAR | Remarks
Labour Cost | 0 | 13407699.97 | 13407699.97 | 52933199.09 | 67482151.92 | 14548952.83
Overtime | 0 | 787163.23 | 787163.23 | 4843543.86 | 3935816.15 | -907727.71
Incentive Provision | 0 | 2262957.49 | 2262957.49 | -1304713.72 | 11314787.45 | 12619501.17
Stores | 4185135.51 | 7130561.5 | 2945425.99 | 29987791.85 | 37708465.5 | 7720673.65
Major Repairs | 670721.61 | 3767889.76 | 3097168.15 | 17190951.45 | 19411921.52 | 2220970.07
Contractors | -532743.35 | 1848208.8 | 2380952.15 | 3992732.46 | 9194556.69 | 5201824.23
Other Cost | 80546.96 | 225133 | 144586.04 | 758072.88 | 1204667.5 | 446594.62
TOTAL | 4403660.73 | 29429613.75 | 25025953.02 | 108401577.87 | 150252366.73 | 41850788.86
Planned Weekend/Public Holiday Work
Description |  |  |  |  | Done | Not Done | Remarks
Plant - Run production and clean mud at 82 dam | [5 empty] | x | Dam cleaning job was cancelled due to shortage of info on method statement
Boilermakers - replace liners on tip 1 and fix doors at MCC1 |  |  |  |  | x
Electricians - Install new supply cable at MS41; painting substation floor; Install power supply at MS170 & extend leaky feed at 110 area |  |  |  |  | x
Drills - Support production and perform housekeeping |  |  |  |  | x
Mechanics - Support production; Housekeeping; UV66 maintenance; Fix grease systems and oil leaks |  |  |  |  | x
Utility - Maintenance on LDO408; Fix RORO carriers; closing outstanding job cards |  |  |  |  | x
Strata - Support production |  |  |  |  | x
Itireleng - maintenance on fire system at Graben |  |  |  |  | x
| Fri | Mon | Tue | Wed | Thur | Average
DT | 91% | 97% | 99% | 90% | 91% | 93.6%
FL | 74% | 100% | 100% | 90% | 84% | 89.6%
HD | 82% | 96% | 100% | 96% | 95% | 93.8%
RT | 98% | 100% | 95% | 94% | 98% | 97%
SR | 97% | 100% | 100% | 99% | 83% | 95.8%
TMM Status SOS (Friday Morning) : | [12 empty] | 5042
Plan
HD | 6 | 6
RT | 6 | 5 | RT43 Strata
DT | 9 | 9
FL | 6 | 5 | FL87 steering
SR | 6 | 5 | SR45 tyre
Charge up UV`s | 3 | 3
RORO/Flat deck UV`s | 3 | 2 | UV54 steering
Weekly Primary TMM Maintenance Overview
Challenges

## Compliance report
Weekly Asset Care Compliance Report
Don’t change Formula's
| Week Ending | 2025-11-13
| Shaft / Area | NCHW II UG
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Unit late for service (y/n) | Unit book back on time after service(y/n) |  | Week-end Service | Reasons for Non-Compliance
| DT | 3 | 3 | 100% | 100%
| FL | 0 | 0 |  | 100%
| HD | 3 | 3 | 100% | 100%
| RT | 2 | 2 | 100% | 100%
| SR - Service Compliance | 0 | 0 |  | 100%
| Support Equipment | 10 | 5 | 50% | 100% |  |  |  |  | LDO553 on breakdown; LDO580 was not brought in for service; UV54 planned to be serviced tonight; UV139 rescheduled; LDO634 planned for weekend
| SR - Weekly Inspection | 8 | 8 | 100% | 100%
Service Pre-Inspection
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Work order number | Remarks
| DT | 0 | 0 |  | 95%
| FL | 0 | 0 |  | 95%
| HD | 3 | 3 | 100% | 95%
| RT | 2 | 2 | 100% | 95%
| SR - Service Compliance | 1 | 1 | 100% | 95%
| Support Equipment | 6 | 4 | 66.67% | 95%
Condition monitoring / Oil samples
| Fleet / Equipment | Engine - Plan | Engine- Received | Transmission - Plan | Transmission - Receive | Axle - plan | Axle - Receive | % Compliance | Reasons for Non-Compliance |  |  | Paperwork Correct | Paperwork Incorrect | Urgent Oil Samples | Workorder Generated
| DT | 3 | 3 |  |  |  |  | 100% | [5 empty] | 1 | 1885128
| FL | 0 | 0 | [10 empty] | 0
| HD | 0 | [11 empty] | 0
| RT | 0 | [11 empty] | 0
| SR | 0 | [11 empty] | 0
| Support Equipment | 10 | 5 |  |  |  |  | 50% | [5 empty] | 0 | UV0102 WILL BE SERVICE TONIGHT ,LD0553 CHASSIC CRACKED ,LD0580 I ASK THEM TO BRING THE MACHINE BUT NEVER REACH
Remember Readings
Oil Filtration
| Equipment nr | Oil Type | Start Reading | End Reading | Comments |  | ISO Standard
FA0007 | DT0157 | Multigrade | 11 / 05 /0 | ,17/12/08
| DT0169 | Multigrade | 11 / 6 /0 | ,17/12/09
| DTO17O | Multigrade | ,10/04/02 | ,17 / 15 / 14
FA0001
| Inspection done by: | Planned Over-Inspections | Total Number of Inspections Completed | Corrective Work | Wo Number | % Completed | Remarks for not comply
| UTILITY FOREMAN | 6 | 4 |  |  | 66.67%
| MECHANIC FOREMAN | 6 | 6 |  |  | 100%
| DRILLS FOREMAN | 5 | 5 |  |  | 100%
| Engineer | 1 | 1 |  |  | 100%
| Electrical Foreman | 4 | 4 |  |  | 100%
| Plant Foreman | 7 | 7 |  |  | 100%
| GES Plant | 1 | 1 |  |  | 100%
| GES TMM | 1 | 1 |  |  | 100%
| Equipment ID | Date of Inspection | Inspection Performed by | Findings and Defects Completed |  |  | Additional Follow-up Work |  |  | WO No. | Status
| RT0038 | 11/11/2025 | Shaied | IO |  |  | None
| HD0046 | 11/11/2025 | Shaied | IO |  |  | None |  |  | 1883353
| RT0040 | 12/11/2025 | Shaied | IO |  |  | None
| HD0064 | 13/11/2025 | Shaied | IO |  |  | None
| N2 U/G Silo system | 10/11/2025 | Lebogang | In Order |  |  | None |  |  | 1869874
| Graben South Jaw crusher | 10/11/2025 | Lebogang | In Order |  |  | None |  |  | 1871824
| Lifting tackle monthly inspection | 11/11/2025 | Lebogang | In Order |  |  | None |  |  | 1872281
| Lever hoist monthly inspection | 11/11/2025 | Lebogang | 3 lever hoists damaged |  |  | Send for repairs |  |  | 1872543
| Fire extinguisher inspection | 12/11/2025 | Lebogang | In Order |  |  | None |  |  | 1872550
| U/G Plant overinspection | 13/11/2025 | Lebogang | In Order |  |  | Mere cleaning to be done at Graben plant |  |  | 1869995
| Chain block monthly inspection | 11/11/2025 | Lebogang | In Order |  |  | None |  |  | 1872281
| HD0067 | 08/11/2025 | Roy | IO |  |  | IO |  |  | 1871785
| HD0046 | 10/11/2025 | Roy | IO |  |  | IO |  |  | 1873114
| RT0038 | 11/11/2025 | Roy | Fuel system contaminated |  |  | Clean fuel tank, replaced lift pump & engine oil cooler. |  |  | 1873180
| RT0043 | 12/11/2025 | Roy | IO |  |  | IO |  |  | 1872503
| HD0064 | 13/11/2025 | ROY | IO |  |  | IO |  |  | 1871704
| LD0576 | 10/11/2025 | BANGO | BRAKE CALLIPER FAULTY |  |  | RH HAND NEW CALLIPER REPLACED AND LH STILL WAITING PARTS |  |  | 1872245
| LD0594 | 13/11/2025 | SHAUN | VEHICLE HAS SCRATCH |  |  | ACCIDENT WAS REPORTED ALREADY BEFORE THE SERVICE |  |  | 1877860
| LD0636 | 12/11/2025 | REA | IO |  |  | IO |  |  | 1881241
| LD0621 | 11/11/2025 | ZEE | IO |  |  | IO |  |  | 1881240
| FL0114-250HRS Service | 07/11/2025 | Wally | IO |  |  | IO |  |  | 1880720
| DT0157-500hrs Service | 08/11/2025 | Wally | IO |  |  | IO |  |  | 1866880
| DT00169- 250HRS Service | 09/11/2025 | Wally | IO |  |  | IO |  |  | 1841733
| DT0099-1000hrs | 10/11/2025 | Wally | IO |  |  | IO |  |  | 1872242
| DT0170-250hrs service | 10/11/2025 | Wally | IO |  |  | IO |  |  | 1856111
| CR0187 | 08/11/2025 | Wally | IO |  |  | IO |  |  | 1856109
I

## Quality report
Weekly Asset Care Compliance Report Nchwaning II UG
| Week Ending | 2025-11-13 | [6 empty] | NB: PLEASE DO NOT EDIT ON YELLOW COLUMN
| Shaft / Area | Nch II U/G
Weekly Quality Service Report
|  |  | Mining |  |  |  | 51.92% | Engineering | [5 empty] | 67.31%
| Schedule Date | TMM Unit Number | Actual Time Available In Workshop - < 7:00 AM | 07:00 AM - 50% 08:00 AM - 25% 09:00 AM - 0% | Machine Clean for Maintenance | No - 0% Yes - 50% |  | Pre inspection & Operator Engagement - 3 Days Before Service Done | No - 0% Yes - 25% | Actual Service Duration - Plan 6 Hours | 6Hrs - 50% 5Hrs - 40% 4Hrs - 30% 3Hrs - 20% 2Hrs - 10% 1Hrs - 0% | Machine Tested and Over Inspected by Supervisor | No - 0% Yes - 25% |  | Completed Service Workorder number | Actual Hrs on service date
1 | 2025-11-07 | DT0157 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
2 | 2025-11-07 | HD0035 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | No | 0% | 75%
3 | 2025-11-07 | RT0040 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
4 | 2025-11-07 | UV0054 |  |  |  |  | 0% | [6 empty] | 0%
5 | 2025-11-07 | LD0553 |  |  |  |  | 0% | [6 empty] | 0% | Breakdown
6 | 2025-11-08 | LD0634 |  |  |  |  | 0% | [6 empty] | 0%
7 | 2025-11-09 | LD0636 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
8 | 2025-11-10 | DT0170 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
9 | 2025-11-10 | HD0046 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
10 | 2025-11-10 | LD0576 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
11 | 2025-11-11 | DT0169 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6HRS | 50% | Yes | 25% | 100%
12 | 2025-11-11 | RT0038 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
13 | 2025-11-11 | LD0580 |  |  |  |  | 0% | [6 empty] | 0%
14 | 2025-11-12 | HD0064 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
15 | 2025-11-12 | UV0102 | 20:00 | 25% | Yes | 50% | 75% | Yes | 25% | 4hrs | 30% | Yes | 25% | 80%
16 | 2025-11-12 | LD0621 | 07h00 | 50% | Yes | 50% | 100% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
17 | 2025-11-13 | HD0065 | 07h00 | 50% | Yes | 50% | 100% | Yes | 25% | 6 hrs | 50% | Yes | 25% | 100%
18 | 2025-11-13 | UV0139 |  |  |  |  | 0% | [6 empty] | 0%
19 | 2025-11-13 | LD0594 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
20 | [6 empty] | 0% | [6 empty] | 0%
21 | [6 empty] | 0% | [6 empty] | 0%
22 | [6 empty] | 0% | [6 empty] | 0%
23 | [6 empty] | 0% | [6 empty] | 0%
24 | [6 empty] | 0% | [6 empty] | 0%
25 | [6 empty] | 0% | [6 empty] | 0%
26 | [6 empty] | 0% | [6 empty] | 0%
27 | [6 empty] | 0% | [6 empty] | 0%
28 | [6 empty] | 0% | [6 empty] | 0%
29 | [6 empty] | 0% | [6 empty] | 0%
30 | [6 empty] | 0% | [6 empty] | 0%
31 | [6 empty] | 0% | [6 empty] | 0%
32 | [6 empty] | 0% | [6 empty] | 0%
33 | [6 empty] | 0% | [6 empty] | 0%
34 | [6 empty] | 0% | [6 empty] | 0%

## Service schedule
Asset Care Service Compliance
| Week: | 07-13 Nov 2025
| 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13
Equip type | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
DT
FL
HD
RT
SR
Support
Outstanding
Compressor's
Over Inspections
FM Drill: |  |  |  | FM Mech:
FM Elect: |  |  |  | GES:
ENG: |  |  |  | MO:

## Fermel Weekly
N 2
No | Area / Owner | TMM type | TMM No. | Breakdown | Comment | OEM Assistance Required |  | Utility Machine | Total | Breakdown | Availabile
| RORO UV'S FERMEL | [6 empty] | Maverick Dble Cab STD Load Bin | 13 | 2 | 84.62%
2 | BRP/Logistics | Liberator Roll On Roll Off | UV0054 |  | Available |  |  | Maverick Man Lift | 4 | 1 | 75%
3 | BRP/Logistics | Liberator Roll On Roll Off | UV0059 |  | Available |  |  | Liberator Roll On Roll Off | 6 | 1 | 83.33%
4 | Roadways | Liberator Roll On Roll Off | UV0061 | During testing, moisture was detected in the diesel fuel system, the affected fluids will need to be fully drained from tank, and the filters replaced. The diesel was drained and the slugge at the bottom of the tank was cleaned then what is outstanding is to replace the strainer, water trap and the diesel filter.The machine is in order just need to be taken underground to drain the hyrdaulic oil and refill. | Not Available |  |  | Placer dumper | 1 | 0 | 100%
5 | BRP/Logistics | Liberator Roll On Roll Off | UV0118 |  | Available |  |  | Maverick king Cab c/w Crane | 3 | 0 | 100%
6 | BRP/Logistics | Fermel Placer Dumper | UV0119 |  | Available |  |  | Maverick Single cab Jam Pot | 1 | 0 | 100%
7 | BRP/Logistics | Liberator Roll On Roll Off | UV0120 |  | Available |  |  | Maverick 12 Man Trooper | 3 | 1 | 66.67%
8 | BRP/Logistics | Liberator Roll On Roll Off | UV0133 | The wire from wiper motor got disconnected and made contact with the harness then there was smoke.Fermel is still trying to locate the harness then we will . | Not Available |  |  | Scaler | 8 | 0 | 100%
| MAVERICK UV'S | [6 empty] | Toyota landcuiser ambulance | 1 | 0 | 100%
10 | Williams /drill mec | Maverick King Cab NO Crane | UV0069 |  | Available |  |  | Maverick king Cab with no Crane | 2 | 1 | 50%
11 | Kal Tire | Maverick King Cab NO Crane | UV0072 |  | Available |  |  | Toyota landcruiser | 36 | 2 | 94.44%
12 | Williams | Maverick king Cab c/w Crane | UV0087 |  | Available |  |  |  | 78 | 8 | 89.74%
13 | Fitters | Maverick king Cab c/w Crane | UV0090 | The speed ring was successfully removed from LD0448, and a seal PR has been created. All parts were replaced there is a challenge in starting busy replacing injectors. | Not Available |  | PR 25001149
14 | Gae | Maverick king Cab c/w Crane | UV0092 |  | Available
15 | Sanitation | Maverick Single cab Jam Pot | UV0102 |  | Available
MAVERICK LDO'S
17 |  |  | LD0378
18 | Roadways | Maverick Dble Cab STD Load Bin | LD0407 |  | Available
19 | Williams /drill mec | Maverick Dble Cab STD Load Bin | LD0408 |  | Available
20 | Mining/28 section | Maverick Dble Cab STD Load Bin | LD0411 |  | Available
21 | Technicians | Maverick Dble Cab STD Load Bin | LD0414 |  | Available |  | Labour for the week including Nightshift
22 | Themba fire fighters | Maverick Dble Cab STD Load Bin | LD0415 |  | Available |  | Foreman | 1 of 1
23 | Boilermakers | Maverick Dble Cab STD Load Bin | LD0419 |  | Available |  | Chargehand | 1 of 1
24 | Technicians | Maverick Dble Cab STD Load Bin | LD0426 | The engine has siezured therefore going to replace cylinder head parts and the order has been placed and the buyer has send the order to the OEM. | Not Available |  | Mechanics | 9 of 9
25 | Gae | Maverick Dble Cab STD Load Bin | LD0448 | The machine was initially reported with a noisy differential caused by a faulty CV joint. At that time, no repairs were planned, as Team 448 was scheduled to receive a new bakkie and the current machine was set to be scrapped and has been moved to surface decline parking. As per senior instruction: The TRM oil cooler has been removed and was fitted on LD450. The RH and LH axle brackets have been removed and allocated to complesion on UV87 | Out of production |  | Auto Electrician | 3 of 3
26 | Explosive | Maverick Dble Cab STD Load Bin | LD0450 |  | Available |  | Semi skilled | 3 of 3
27 | Capital graben | Maverick Dble Cab STD Load Bin | LD0508 | Replacement of engine is done,the outstanding work is to fix head light with door sensor.that was not done because the focus is on the Roro passenger carriers by fixing rotation light,fixing the plugs with the door sensors.And also testing the door sensor of the carrier, | Not Available |  | Leaners
28 | Gae | Maverick Dble Cab STD Load Bin | LD0509 |  | Available
29 | Utility | Maverick Dble Cab STD Load Bin | LD0513 | LD0513 is currently on surface, parked at the decline yard, and ready to be scrapped. However, we are in the process of removing the front axle to be allocated to LD0532. This diff fron 513 will be used on LD0532 the 1st differential had previously been utilized for Unit 477, and the second differential was recently planned for UV87. | Out of production
30 | Capital graben | Maverick Dble Cab STD Load Bin | LD0519 |  | Available
32
33
34
35
36
37
| MAVERICK LDO'S TROPPER | [5 empty] | DELAY:
39 | Fitters | Maverick 12 Man Trooper | LD0477 |  | Available
40 | Mining/28 section | Maverick 12 Man Trooper | LD0523 |  | Available
41 | Construction | Maverick 12 Man Trooper | LD0532 |  | Available | 1799543
42 | MAVERICK UV'S MANLIFTS | [5 empty] | PRIORITY FOR THE NEXT SHIFT
43 | Geologist | Maverick Man Lift | UV0077 | an email from GES (The Fermel tech has rebuild the complete rear harness and this section is now fully operational.However, the front harness is also faulty – intermittent and some wires shorting or not making contact.As Fermel does not have this harness right now in stock, the Fermel tech will be back on-site next week to perform onsite repairs to get machine going,This is interim repairs to assist us, until Fermel get the correct harness the first week in October but we are already second week no harness has been availed.) | Not Available
44 | Survey | Maverick Man Lift | UV0098 |  | Available
45 | Survey | Maverick Man Lift | UV0099 |  | Available
46 | Geologist | Maverick Man Lift | UV0123 |  | Available |  | SERVICE UPDATES
TOYOTA CRUISER LDO'S
47 | Ambulance | Toyota Cruiser 4x4 emergency vehicle | LD0 341 |  | Available
48 | Capital graben | Toyota Cruiser 4x4/Trimming-Connie | LD0 553 |  | Available
49 | Lebolo/2west2body | Toyota Cruiser 4x4/mining -Lebelo | LD0 554 |  | Available
50 | Connie Trimming | Toyota Cruiser 4x4/Trimming-Connie | LD0 557 |  | Available
51 | Fitters w/shop | Toyota Cruiser 4x4/fitter plant-Lebogang | LD0 575 |  | Available
52 | Electrical w/shop | Toyota Cruiser 4x4 /electrician-Hansie | LD0 576 | Both brake caliper has seizured and we have replaced one side then waiting for the other side which was incorrect order. | Not Available
53 | Connie Mining | Toyota Cruiser 4x4/mining-Connie | LD0 577 |  | Available
54 | Peace | Toyota Cruiser 4x4/mining -portgter | LD0 578 |  | Available
55 | Christo | Toyota Cruiser 4x4/mining-christo | LD0 579 |  | Available
56 | Training Center | Toyota Cruiser 4x4/training center | LD0 580 |  | Available
57 | Potgieter | Toyota Cruiser 4x4/Mining 28 section | LD0 581 |  | Available
5 |  |  |  |  | Available
55 |  |  |  |  | Available
56
58 |  |  |  |  | Available
59 |  |  |  |  | Available
TOYOTA CRUISER LDO'S
61 | Construction | aard-uv60 | UV0042 | Please note that the machine is currently underground and has been listed for scrapping. We need to arrange its transfer to surface and proceed with the scrapping process ASAP | Out of production
62 | Duba Utility | aard-uv60-diesel tank | UV0053 |  | Available
63 | Hansie Louw | aard-uv60 | UV0084 |  | Available
64 | Roadways | aard-uv80-water tank truck | UV0121 |  | Available
65 | Capital-Graben | aard-uv80 | UV0130 |  | Available
66 | Construction | aard-uv60 | UV0139 |  | Available
67 | Construction | aard-uv60 | UV0140 |  | Available
68
| SCALER'S |  |  |  | Available
70 | Scaler | Scaler | SR0025 |  | Available
71 | Scaler | scaler | SR0027 |  | Available
72 | Scaler | Scaler | SR0029 |  | Available
73 | Scaler | Scaler | SR0033 |  | Available
74 | Scaler | scaler graben Capital Tel 5013 | SR0036 |  | Available
75 | Scaler | scaler 17upper 74 Portigter | SR0042 |  | Available
76 | Scaler | scaler 17upper 74 Portigter | SR0045 |  | Available
77 | Scaler | scaler graben Capital Tel 5013 | SR0046 |  | Available
| Scaler | Scaler Mining | SR0053 | Gear does not move to nuetral because of high pressure therefore they are going to release the pressure and then we check the conduct of transducer. | Not Available
78 | Scaler | Scaler Mining | SR0054 |  | Available
TOYOTA CRUISER WITH HIAB'S
78 | Life Tmm | Toyota Cruiser 4x4/Utility Duba | LD0 589* |  | Available
79 | Duba Utility | Toyota Cruiser 4x4/Kal Tire | LD0 590* |  | Available
80 | Didi-Boilermaker | Toyota Cruiser 4x4/Kal Tire | LD0 592* |  | Available
81 | Izak Bothman KalTire | Toyota Cruiser 4x4/ | LD0 593* |  | Available
82 | Fitters Lebogang | Toyota Cruiser 4x4/ | LD0 594 | done service | Available
83 | Duba Utility | Toyota Cruiser 4x4/ | LD0 621 |  | Available
84 | Life Tmm | Toyota Cruiser 4x4/ | LD0 633 | Programming for level 9 | Available
TOYOTA CRUISER TROPPER'S
84 | Karl Roadways | Toyota Cruiser 4x4/ | LD0 596 |  | Available
85 | Geologist&Survey | Toyota Cruiser 4x4/ | LD0 605 |  | Available
86 | Mining-Peace | Toyota Cruiser 4x4/ | LD0 629 | Redrill saddle plate to fit m16 bolts and to replase bushes | Not Available
| Mining | Toyota Cruiser 4x4/ | LD0 649 |  | Available
| Duba Utility | Toyota Cruiser 4x4/ | LD0 650 |  | Available
TOYOTA CRUISER WITHOUT HIAB'S
87 | William Tel:5429 | Toyota Cruiser 4x4/ | LD0 591 |  | Available
88 | Duba Utility | Toyota Cruiser 4x4- single cap | LD0 621* |  | Available
89 | Electrician tel:5416 | Toyota Cruiser 4x4/ | LD0 623 |  | Available
90 | Electrician tel:5416 | Toyota Cruiser 4x4/ drill rod carrier | LD0 630* |  | Available
91 | William Tel:5429 | Toyota Cruiser 4x4/ drill rod carrier | LD0 631 |  | Available
92 | Boilers | Toyota Cruiser 4x4/ drill rod carrier | LD0 634* |  | Available
93 | Izak Botham | Toyota Cruiser 4x4/ drill rod carrier | LD0 636* |  | Available
| Strata team | CRUISER SINGLE CAP Hiab | LD0642 |  | Available
| Manyafunyafu | CRUISER SINGLE CAP Hiab | LD0647 |  | Not Available
|  | CRUISER SINGLE CAP Hiab | LD0648 |  | Not Available
|  | CRUISER SINGLE CAP Hiab | LD0658 |  | Available

## Blocked chutes
0 | Details | FEEDER BELT CHUTE |  |  | TIPS 1&2 | [5 empty] | Area xyz
Supervisor/artisan who assisted with unblocking
01/11/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
02/11/2025 | Reason for blockage
Time of blockage
| Supervisor/artisan who assisted with unblocking | J Benson | T.K Mosiane | Xaba | J Benson | T.K Mosiane | Xaba | J Benson | T.K Mosiane | Xaba
03/11/2025 | Reason for blockage | Big rock wedge | No blockages | No Blockages | No Blockages | No blockages | No Blockages | No Blockages | No blockages | No Blockages
| Time of blockage | 13h14-13h24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
04/11/2025 | Supervisor/artisan who assisted with unblocking | J Benson | T.K Mosiane |  | J Benson | T.K Mosiane |  | J Benson | T.K Mosiane
| Reason for blockage | No Blockages | No blockages |  | No Blockages | No blockages |  | No Blockages | No blockages
| Time of blockage | N/A | N/A |  | N/A | N/A |  | N/A | N/A
| Supervisor/artisan who assisted with unblocking | Ti Boshowe | T.K Mosiane | Xaba | Ti Boshowe | T.K Mosiane | Xaba | Ti Boshowe | T.K Mosiane | Xaba
05/11/2025 | Reason for blockage | No Blockages | No blockages | No Blockages | No Blockages | No blockages | No Blockages | No Blockages | No blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | T.K Mosiane | Xaba | J Benson | T.K Mosiane | Xaba | J Benson | T.K Mosiane | Xaba
06/11/2025 | Reason for blockage | No Blockages | No blockages | No Blockages | No Blockages | No blockages | No Blockages | No Blockages | No blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | T.K Mosiane |  | J Benson | T.K Mosiane |  | J Benson | T.K Mosiane
07/11/2025 | Reason for blockage | Big flat rock wedge in the middle of chute. | No blockages |  | No Blockages | No blockages |  | No Blockages | No blockages
| Time of blockage | 13h15-14h01 | N/A |  | N/A | N/A |  | N/A | N/A
Supervisor/artisan who assisted with unblocking
08/11/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
09/11/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
10/11/2025 | Reason for blockage
Time of blockage
11/11/2025 | Supervisor/artisan who assisted with unblocking |  |  | J Benson |  |  | J Benson |  |  | J Benson
| Reason for blockage |  |  | No Blockages |  |  | No Blockages |  |  | No Blockages
| Time of blockage |  |  | N/A |  |  | N/A |  |  | N/A
12/11/2025 | Supervisor/artisan who assisted with unblocking | xaba | T.K Mosiane | L Smous | Xaba | T.K Mosiane | L Smous | Xaba | T.K Mosiane | L Smous
| Reason for blockage | No Blockages | No blockages | Big rocks | No blockage | No blockages | No Blockages | No blockage | No blockages | No Blockages
| Time of blockage | N/A | N/A | 00:09 - 00:20 | N/A | N/A | N/A | N/A | N/A | N/A
13/11/202 | Supervisor/artisan who assisted with unblocking | xaba | T.K Mosiane | L Smous | Xaba | T.K Mosiane | L Smous | Xaba | T.K Mosiane | L Smous
| Reason for blockage | No Blockages | No blockages | No Blockages | No blockage | No blockages | No Blockages | No blockage | No blockages | No Blockages
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
15/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
16/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
17/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
18/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
19/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
20/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
21/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
22/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
23/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
24/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
25/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
26/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
27/11/202 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
28/11/202 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
29/11/202 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
30/11/202 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
31/11/202 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage